SYRIA RECOVERY TRUST FUND

STANDARD BIDDING DOCUMENTS

Procurement of Works

June 2014

Preface

This Standard Bidding Document for Procurement of Works has been prepared for use in contracts financed by the Syria Recovery Trust Fund (SRTF) through the SRTF Yönetim Hizmetleri A. Ş., Turkey (translated: SRTF Management Services JSC) (Syria A.S.), involving contracts valued at at least one million Euro.  It is based on the standard World Bank bidding document for procurement of Works (in the case of the original document, this SBD would apply to works with a value up to USD 10 million), revision 2012, and after adaptation, including some simplification, it is consistent with the  Procurement Guidelines of SRTF. This document is intended as a model in the award of admeasurement (unit prices or unit rates in a bill of quantities) and lump sum types of contracts, which are the most common in Works contracting.

This Standard Bidding Document for Procurement of Works is to be used when a prequalification process has not taken place before bidding and, therefore, post-qualification applies.

This document includes also a lump sum contract. Lump sum contracts are used in particular for buildings and other forms of construction where the Works are well defined and are unlikely to change in quantity or specification, and where encountering difficult or unforeseen site conditions (for example, hidden foundation problems) is unlikely.  Lump sum contracts should be used for Works that can be defined in their full physical and qualitative characteristics before bids are called, or where the risks of substantial design variations are minimal, such as bus shelters or school ablution units.  In lump sum contracts, the concept of priced “activity schedules” is used, to enable payments to be made on the basis of percentage completion of each activity.

Summary Description

SBD for Procurement of Works

PART 1 – BIDDING PROCEDURES

Section I.	Instructions to Bidders (ITB)

This Section provides relevant information to help Bidders prepare their bids. Information is also provided on the submission, opening, and evaluation of bids and on the award of Contracts.  Section I contains provisions that are to be used without modification.

Section II.	Bid Data Sheet (BDS)

This Section includes of provisions that are specific to each procurement and that supplement Section I, Instructions to Bidders.

Section III.	Evaluation and Qualification Criteria

This Section includes the criteria to determine the lowest evaluated bid and the qualifications of the Bidder to perform the contract.

Section IV.	Bidding Forms

This Section includes the forms which are to be completed by the Bidder and submitted as part of his Bid

Section V.	Eligible Countries

This Section includes the forms which are to be completed by the Bidder and submitted as part of his Bid

.

PART 2 – WORKS REQUIREMENTS

Section VI. 	Works Requirements

This Section contains the Specification, the Drawings, and supplementary information that describe the Works to be procured.

PART 3 – CONDITIONS OF CONTRACT AND CONTRACT FORMS

Section VII.	General Conditions of Contract (GCC)

This Section contains the general clauses to be applied in all contracts.  The text of the clauses in this Section shall not be modified.

Section VIII.	Particular Conditions of Contract (PCC)

This Section consists of Contract Data and Specific Provisions which contains clauses specific to each contract. The contents of this Section modify or supplement, the General Conditions and shall be prepared by the Employer.

Section IX.	Contract Forms

This Section contains forms which, once completed, will form part of the Contract. The forms for Performance Security and Advance Payment Security, when required, shall only be completed by the successful Bidder after contract award.

Attachment:	 Invitation for Bids

An “Invitation for Bids” form is provided at the end of the Bidding Documents for information.

PROCUREMENT DOCUMENTS

Bidding Document for

Procurement of Works

Procurement of

ICB No:_____________

[insert reference number as per procurement plan]

Project:______________

Employer:_____________

Country:_____________

Issued on: ____________

[insert date when document was issued to bidders]

Standard Bidding Document

Table of Contents

PART 1 – Bidding Procedures	1-1

Section 1 - Instructions to Bidders	1-3

Section II - Bid Data Sheet (BDS)	1-27

Section III - Evaluation and Qualification Criteria	1-33

Section IV - Bidding Forms	1-45

Section V - Eligible Countries	1-71

PART 2 – Works Requirements	2-1

Section VI - Works Requirements	2-3

PART 3 – Conditions of Contract and Contract Forms	3-1

Section VII.  General Conditions of Contract	3-3

Section VIII.  Particular Conditions of Contract	3-29

Section IX - Contract Forms	3-33

PART 1 – Bidding Procedures

Section 1 - Instructions to Bidders

Table of Clauses

A.	General	5

1.	Scope of Bid	5

2.	Source of Funds	5

3.	Corrupt and Fraudulent Practices	6

4.	Eligible Bidders	7

5.	Eligible Materials, Equipment and Services	9

B.	Contents of Bidding Document	9

6.	Sections of Bidding Document	9

7.	Clarification of Bidding Document, Site Visit, Pre-Bid Meeting	10

8.	Amendment of Bidding Document	11

C.	Preparation of Bids	11

9.	Cost of Bidding	11

10.	Language of Bid	11

11.	Documents Comprising the Bid	12

12.	Letter of Bid and Schedules	12

13.	Alternative Bids	12

14.	Bid Prices and Discounts	13

15.	Currencies of Bid and Payment	14

16.	Documents Comprising the Technical Proposal	14

17.	Documents Establishing the Qualifications of the Bidder	14

18.	Period of Validity of Bids	14

19.	Bid Security	15

20.	Format and Signing of Bid	16

D.	Submission and Opening of Bids	17

21.	Sealing and Marking of Bids	17

22.	Deadline for Submission of Bids	18

23.	Late Bids	18

24.	Withdrawal, Substitution, and Modification of Bids	18

25.	Bid Opening	18

E.	Evaluation and Comparison of Bids	20

26.	Confidentiality	20

27.	Clarification of Bids	20

28.	Deviations, Reservations, and Omissions	20

29.	Determination of Responsiveness	20

30.	Nonconformities, Errors, and Omissions	21

31.	Correction of Arithmetical Errors	22

32.	Conversion to Single Currency	22

33.	Margin of Preference	22

34.	Subcontractors	22

35.	Evaluation of Bids	23

36.	Comparison of Bids	24

37.	Qualification of the Bidder	24

38.	Employer’s Right to Accept Any Bid, and to Reject Any or All Bids	24

F.	Award of Contract	24

39.	Award Criteria	24

40.	Notification of Award	24

41.	Signing of Contract	26

42.	Performance Security	26

43.	Adjudicator	26

Section I - Instructions to Bidders

| General |
| --- |
| Scope of Bid | In connection with the Invitation for Bids specified in the Bid Data Sheet (BDS), the Employer (hereinafter called also Recipient or Implementing entity or Beneficiary), as specified in the BDS, issues these Bidding Documents for the procurement of the Works as specified in Section VI, Works Requirements. The name, identification, and number of this bidding are specified in the BDS. |
|  | Throughout this Bidding Document: (a) the term “in writing” means communicated in written form and delivered against receipt; (b) except where the context requires otherwise, words indicating the singular also include the plural and words indicating the plural also include the singular; and (c) “day” means calendar day. |
| Source of Funds | The Recipient has received financing (hereinafter called “funds”) from the Syria Recovery Trust Fund (hereinafter called “SRTF”) through SRTF Yönetim Hizmetleri A. Ş., Turkey (translated: SRTF Management Services JSC) (hereinafter called “Syria A.S.”) toward the cost of the project named in the BDS. The Recipient intends to apply a portion of the funds to eligible payments under the contract for which these Bidding Documents are issued. |
|  | Payments by SRTF will be made only at the request of the Recipient and upon approval by Syria A.S. or SRTF in accordance with the terms and conditions of the financing agreement between the Recipient and Syria A.S. (hereinafter called the Financing Agreement), and will be subject in all respects to the terms and conditions of that Financing Agreement. The Financing Agreement prohibits a withdrawal from the financing account for the purpose of any payment to persons or entities, or for any import of goods, if such payment or import, to the knowledge of SRTF, is prohibited by decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations. No party other than the Recipient shall derive any rights from the Financing Agreement or have any claim to the funds. |
| Corrupt and Fraudulent Practices | It is SRTF’s policy to require that Recipients, as well as bidders, suppliers, and contractors and their agents (whether declared or not), personnel, subcontractors, sub-consultants, service providers and suppliers under SRTF-financed contracts, observe the highest standard of ethics during the procurement and execution of such contracts. In pursuance of this policy, SRTF: (a) defines, for the purposes of this provision, the terms set forth below as follows: (i) “corrupt practice” is the offering, giving, receiving or soliciting, directly or indirectly, of anything of value to influence improperly the actions of another party; (ii) “fraudulent practice” is any act or omission, including a misrepresentation, that knowingly or recklessly misleads, or attempts to mislead, a party to obtain a financial or other benefit or to avoid an obligation; (iii) “collusive practice” is an arrangement between two or more parties designed to achieve an improper purpose, including to influence improperly the actions of another party; (iv) “coercive practice” is impairing or harming, or threatening to impair or harm, directly or indirectly, any party or the property of the party to influence improperly the actions of a party; (v) “obstructive practice” is (aa) deliberately destroying, falsifying, altering or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a SRTF investigation into allegations of a corrupt, fraudulent, coercive or collusive practice; and/or threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation; or (bb) acts intended to materially impede the exercise of SRTF’s inspection and audit rights provided for under sub-clause 3.1 (e) below. (b) will reject a proposal for award if it determines that the bidder recommended for award has, directly or through an agent, engaged in corrupt, fraudulent, collusive, coercive or obstructive practices in competing for the contract in question; (c) will cancel the portion of the financial support allocated to a contract if it determines at any time that representatives of the Recipient of the financial support engaged in corrupt, fraudulent, collusive, or coercive practices during the procurement or the execution of that contract, without the Recipient having taken timely and appropriate action satisfactory to SRTF to address such practices when they occur. In further pursuance of this policy, Bidders shall permit and shall cause its agents (whether declared or not), sub-contractors, sub-consultants, service providers, or suppliers and any personnel thereof, to permit SRTF to inspect all accounts, records and other documents relating to any prequalification process, bid submission, and contract performance (in the case of award), and to have them audited by auditors appointed by SRTF. |
| Eligible Bidders | A Bidder, and all parties constituting the Bidder, may have the nationality of any country, subject to the restrictions specified in Section V, Eligible Countries. A Bidder shall be deemed to have the nationality of a country if the Bidder is a citizen or is constituted, incorporated, or registered and operates in conformity with the provisions of the laws of that country. This criterion shall also apply to the determination of the nationality of proposed subcontractors or suppliers for any part of the Contract A Bidder may be a firm that is a private entity, or a government-owned entity—subject to ITB 4.1—or any combination of them in the form of a joint venture (JV), under an existing agreement, or with the intent to enter into such an agreement supported by a letter of intent. In the case of a joint venture, all members shall be jointly and severally liable for the execution of the Contract in accordance with the Contract terms. The JV shall nominate a Representative who shall have the authority to conduct all business for and on behalf of any and all the members of the JV during the bidding process and, in the event the JV is awarded the Contract, during contract execution. Unless specified in the BDS, there is no limit on the number of members in a JV. |
|  | Bidders may submit bids, if none of the following reasons for exclusion apply: (i) Participation of a bidder (or any of its personnel) is ruled out by sanctions issued by the UN Security Council, the EU, the US or any other Donor supporting the SRTF. The list of Donors supporting the SRTF is included in Section V, Eligible countries; or (ii) the bidder is or was involved as a consultant in the preparation or implementation of the Project. The same applies to an enterprise or an individual that is closely connected to the bidder under a company group or a similar business link , or to several enterprises or individuals associated correspondingly; or (iii) the bidder is legally barred from the procurement process in its own or any Donor country or the country of the contracting agency on the grounds of previous violations of regulation on fraud and corruption; if the bidder is legally barred from the procurement process in Syria, the exclusion shall only be considered, if it is officially recognized by the National Coalition; or (iv) the bidder or sub-contractors to be contracted for considerable portions of the contract are enterprises economically intertwined with the contracting agency (Implementing Entity) in the host country and/or state controlled enterprises that are not legally or financially independent. A Bidder and its sub-contractors may not be engaged in financing terrorism, including providing financing or support to any persons who are designated by the U.S. Department of Treasury as “Specially Designated Nationals” or subject to sanctions by the EU. A Bidder shall not be under suspension from bidding by the SRTF or the Employer. In the implementation of the project a Bidder must adhere to minimum social standards ("Core Labour Standards") ratified by Syria. |
|  | A Bidder shall provide such evidence of eligibility satisfactory to the Employer, as the Employer shall reasonably request. |
| Eligible Materials, Equipment and Services | The materials, equipment and services to be supplied under the Contract and financed by SRTF may have their origin in any country subject to the restrictions specified in Section V, Eligible Countries, and all expenditures under the Contract will not contravene such restrictions. At the Employer’s request, Bidders may be required to provide evidence of the origin of materials, equipment and services. |
| Contents of Bidding Document |
| Sections of Bidding Document | The Bidding Document consist of Parts 1, 2, and 3, which include all the Sections specified below, and which should be read in conjunction with any Addenda issued in accordance with ITB 8. PART 1 Bidding Procedures Section I - Instructions to Bidders (ITB) Section II - Bid Data Sheet (BDS) Section III - Evaluation and Qualification Criteria Section IV - Bidding Forms Section V - Eligible Countries PART 2 Works Requirements Section VI - Works Requirements PART 3 Conditions of Contract and Contract Forms Section VII - General Conditions of Contract (GCC) Section VIII - Particular Conditions of Contract (PCC) Section IX - Contract Forms |
|  | The Invitation for Bids issued by the Employer is not part of the Bidding Document. |
|  | Unless obtained directly from the Employer or SRTF, the Employer or SRTF is not responsible for the completeness of the Bidding Documents, responses to requests for clarification, the minutes of the pre-Bid meeting (if any), or Addenda to the Bidding Documents in accordance with ITB 8. In case of any contradiction, documents obtained directly from the Employer or from the latest version published on the SRTF web page shall prevail. |
|  | The Bidder is expected to examine all instructions, forms, terms, and specifications in the Bidding Documents and to furnish with its bid all information and documentation as is required by the Bidding Documents. |
| Clarification of Bidding Document, Site Visit, Pre-Bid Meeting | A Bidder requiring any clarification of the Bidding Document shall contact the Employer in writing at the Employer’s address specified in the BDS or raise its inquiries during the pre-bid meeting if provided for in accordance with ITB 7.4. The Employer will respond in writing to any request for clarification by publication on the website www.srtfund.org, provided that such request is received prior to the deadline for submission of bids within a period specified in the BDS. Should the clarification result in changes to the essential elements of the Bidding Documents, the Employer shall amend the Bidding Documents following the procedure under ITB 8 and ITB 22.2. |
|  | The Bidder is advised to visit and examine the Site of Works and its surroundings and obtain for itself on its own responsibility all information that may be necessary for preparing the bid and entering into a contract for construction of the Works. The costs of visiting the Site shall be at the Bidder’s own expense. |
|  | The Bidder and any of its personnel or agents will be granted permission by the Employer to enter upon its premises and lands for the purpose of such visit, but only upon the express condition that the Bidder, its personnel, and agents will release and indemnify the Employer and its personnel and agents from and against all liability in respect thereof, and will be responsible for death or personal injury, loss of or damage to property, and any other loss, damage, costs, and expenses incurred as a result of the inspection. |
|  | If so specified in the BDS, the Bidder’s designated representative is invited to attend a pre-bid meeting. The purpose of the meeting will be to clarify issues and to answer questions on any matter that may be raised at that stage. |
|  | The Bidder is requested, to submit any questions in writing, to reach the Employer not later than one week before the meeting. |
|  | Minutes of the pre-bid meeting, if applicable, including the text of the questions asked by Bidders, without identifying the source, and the responses given, together with any responses prepared after the meeting, will be published on the website www.srtfund.org. Any modification to the Bidding Documents that may become necessary as a result of the pre-bid meeting shall be made by the Employer exclusively through the issue of an addendum pursuant to ITB 8 and not through the minutes of the pre-bid meeting. Nonattendance at the pre-bid meeting will not be a cause for disqualification of a Bidder. |
| Amendment of Bidding Document | At any time prior to the deadline for submission of bids, the Employer may amend the Bidding Documents by issuing addenda. |
|  | Any addendum issued shall be part of the Bidding Documents and shall be published on the web site of the SRTF. The Employer shall also promptly publish the addendum on the Employer’s web page in accordance with ITB 7.1. |
|  | To give prospective Bidders reasonable time in which to take an addendum into account in preparing their bids, the Employer may, at its discretion, extend the deadline for the submission of bids, pursuant to ITB 22.2. |
| Preparation of Bids |
| Cost of Bidding | The Bidder shall bear all costs associated with the preparation and submission of its Bid, and the Employer shall in no case be responsible or liable for those costs, regardless of the conduct or outcome of the bidding process. |
| Language of Bid | The Bid, as well as all correspondence and documents relating to the bid exchanged by the Bidder and the Employer, shall be written in the language specified in the BDS. Supporting documents and printed literature that are part of the Bid may be in another language provided they are accompanied by an accurate translation of the relevant passages in the language specified in the BDS, in which case, for purposes of interpretation of the Bid, such translation shall govern. |
| Documents Comprising the Bid | The Bid shall comprise the following: Letter of Bid and Appendix to Bid, in accordance with ITB 12; completed Schedules, in accordance with ITB 12 and 14: as specified in the BDS; Bid Security or Bid Securing Declaration, in accordance with ITB 19.1; alternative bids, if permissible, in accordance with ITB 13; written confirmation authorizing the signatory of the Bid to commit the Bidder, in accordance with ITB 20.2; documentary evidence in accordance with ITB 17 establishing the Bidder’s qualifications to perform the contract if its Bid is accepted; Technical Proposal in accordance with ITB 16; and any other document required in the BDS. In addition to the requirements under ITB 11.1, bids submitted by a JV shall include a copy of the Joint Venture Agreement entered into by all members. Alternatively, a letter of intent to execute a Joint Venture Agreement in the event of a successful bid shall be signed by all members and submitted with the bid, together with a copy of the proposed Agreement. The Bidder shall furnish in the Letter of Bid information on commissions and gratuities, if any, paid or to be paid to agents or any other party relating to this Bid. |
| Letter of Bid and Schedules | The Letter of Bid and Schedules shall be prepared using the relevant forms furnished in Section IV, Bidding Forms. The forms must be completed without any alterations to the text, and no substitutes shall be accepted except as provided under ITB 20.2. All blank spaces shall be filled in with the information requested. |
| Alternative Bids | Unless otherwise specified in the BDS, alternative bids shall not be considered. |
|  | When alternative times for completion are explicitly invited, a statement to that effect will be included in the BDS, as will the method of evaluating different times for completion. |
|  | Except as provided under ITB 13.4 below, Bidders wishing to offer technical alternatives to the requirements of the Bidding Document must first price the Employer’s design as described in the Bidding Document and shall further provide all information necessary for a complete evaluation of the alternative by the Employer, including drawings, design calculations, technical specifications, breakdown of prices, and proposed construction methodology and other relevant details. Only the technical alternatives, if any, of the lowest evaluated Bidder conforming to the basic technical requirements shall be considered by the Employer. |
|  | When specified in the BDS, Bidders are permitted to submit alternative technical solutions for specified parts of the Works. Such parts will be identified in the BDS and described in Section VI. Works Requirements. The method for their evaluation will be stipulated in Section III. Evaluation and Qualification Criteria. |
| Bid Prices | The prices quoted by the Bidder in the Letter of Bid and in the Schedules shall conform to the requirements specified below. |
|  | The Bidder shall submit a bid for the whole of the works described in ITB 1.1 by filling in prices for all items of the Works, as identified in Section IV. Bidding Forms. In case of admeasurement contracts, the Bidder shall fill in rates and prices for all items of the Works described in the Bill of Quantities. Items against which no rate or price is entered by the Bidder will not be paid for by the Employer when executed and shall be deemed covered by the rates for other items and prices in the Bill of Quantities. |
|  | The price to be quoted in the Letter of Bid, in accordance with ITB 12.1, shall be the total price of the bid. |
|  | Unless otherwise provided in the BDS and the Conditions of Contract, the prices quoted by the Bidder shall be fixed. If the prices quoted by the Bidder are subject to adjustment during the performance of the Contract in accordance with the provisions of the Conditions of Contract, the Bidder shall furnish the indices and weightings for the price adjustment formulae in the Schedule of Adjustment Data in Section IV- Bidding Forms and the Employer may require the Bidder to justify its proposed indices and weightings. Bids are invited for individual lots (contracts).. |
|  | All duties, taxes, and other levies payable by the Contractor under the Contract, or for any other cause, as of the date 28 days prior to the deadline for submission of bids, shall be included in the rates and prices and the total bid price submitted by the Bidder. |
| Currencies of Bid and Payment | The currency(ies) of the bid and the currency(ies) of payments shall be as specified in the BDS. |
|  | Bidders may be required by the Employer to justify, to the Employer’s satisfaction, their local and foreign currency requirements, and to substantiate that the amounts included in the unit rates and prices and shown in the Schedule of Adjustment Data in the Appendix to Bid are reasonable, ,in which case a detailed breakdown of the foreign currency requirements shall be provided by Bidders. |
| Documents Comprising the Technical Proposal | The Bidder shall furnish a Technical Proposal including a statement of work methods, equipment, personnel, schedule and any other information as stipulated in Section IV, Bidding Forms, in sufficient detail to demonstrate the adequacy of the Bidders’ proposal to meet the work requirements and the completion time. |
| Documents Establishing the Qualifications of the Bidder | In accordance with Section III, Evaluation and Qualification Criteria, to establish its qualifications to perform the Contract, the Bidder shall provide the information requested in the corresponding information sheets included in Section IV, Bidding Forms. |
| Period of Validity of Bids | Bids shall remain valid for the period specified in the BDS after the bid submission deadline date prescribed by the Employer in accordance with ITB 22.1. A bid valid for a shorter period shall be rejected by the Employer as nonresponsive. |
|  | In exceptional circumstances, prior to the expiration of the bid validity period, the Employer may request Bidders to extend the period of validity of their bids. The request and the responses shall be made in writing. If a bid security is requested in accordance with ITB 19, it shall also be extended for twenty-eight (28) days beyond the deadline of the extended validity period. A Bidder may refuse the request without forfeiting its bid security. A Bidder granting the request shall not be required or permitted to modify its bid, except as provided in ITB 18.3. |
| Bid Security | The Bidder shall furnish as part of its bid, either a Bid-Securing Declaration or a bid security as specified in the BDS, in original form and, in the case of a bid security, in the amount and currency specified in the BDS. |
|  | A Bid Securing Declaration shall use the form included in Section IV, Bidding Forms. |
|  | If a bid security is specified pursuant to ITB 19.1, the bid security shall be an unconditional guarantee issued by a bank or financial institution (such as an insurance, bonding or surety company) from a reputable source from an eligible country. If the unconditional guarantee is issued by a financial institution located outside the Employer’s Country, the issuing financial institution shall have a correspondent financial institution located in the Employer’s Country to make it enforceable. For the time being the Employer’s country is considered to be Turkey. In the case of a bank guarantee, the bid security shall be submitted either using the Bid Security Form included in Section IV, Bidding Forms . The bid security shall be valid for sixty (8) days beyond the original validity period of the bid, or at least 28 days beyond any period of extension if requested under ITB 18.2. |
|  | If a bid security or Bid Securing Declaration is specified pursuant to ITB 19.1, any bid not accompanied by a substantially responsive bid security or Bid-Securing Declaration shall be rejected by the Employer as non-responsive. |
|  | If a bid security is specified pursuant to ITB 19.1, the bid security of unsuccessful Bidders shall be returned as promptly as possible upon the successful Bidder’s signing the Contract and furnishing the performance security pursuant to ITB 42. |
|  | The bid security of the successful Bidder shall be returned as promptly as possible once the successful Bidder has signed the Contract and furnished the required performance security. |
|  | The bid security may be forfeited or the Bid Securing Declaration executed: if a Bidder withdraws its bid during the period of bid validity specified by the Bidder on the Letter of Bid, , or any extension thereto provided by the Bidder; or if the successful Bidder fails to: sign the Contract in accordance with ITB 41; or furnish a performance security in accordance with ITB 42. |
|  | The bid security or the Bid Securing Declaration of a JV shall be in the name of the JV that submits the bid. If the JV has not been constituted into a legally-enforceable JV, at the time of bidding, the Bid Security or the Bid Securing Declaration shall be in the names of all future members as named in the letter of intent mentioned in ITB 4.1 and ITB 11.2. |
|  | If a bid security is not required in the BDS, and if a Bidder withdraws its bid during the period of bid validity specified by the Bidder on the Letter of Bid, or (b) if the successful Bidder fails to: sign the Contract in accordance with ITB 41; or furnish a performance security in accordance with ITB 42; SRTF may, if provided for in the BDS, declare the Bidder ineligible to be awarded a contract financed by SRTF for a period of time as stated in the BDS. |
| Format and Signing of Bid | The Bidder shall prepare one original of the documents comprising the bid as described in ITB 11 and clearly mark it “Original”. Alternative bids, if permitted in accordance with ITB 13, shall be clearly marked “Alternative”. In addition, the Bidder shall submit copies of the bid in the number specified in the BDS, and clearly mark each of them “Copy.” In the event of any discrepancy between the original and the copies, the original shall prevail. |
|  | The original and all copies of the bid shall be typed or written in indelible ink and shall be signed by a person duly authorized to sign on behalf of the Bidder. This authorization shall consist of a written confirmation as specified in the BDS and shall be attached to the bid. The name and position held by each person signing the authorization must be typed or printed below the signature. All pages of the bid where entries or amendments have been made shall be signed or initialed by the person signing the bid. |
|  | In case the Bidder is a JV, the Bid shall be signed by an authorized representative of the JV on behalf of the JV, and so as to be legally binding on all the members as evidenced by a power of attorney signed by their legally authorized representatives. Any interlineations, erasures, or overwriting shall be valid only if they are signed or initialed by the person signing the bid. |
| Submission and Opening of Bids |
| Sealing and Marking of Bids | The Bidder shall enclose the original and all copies of the bid, including alternative bids, if permitted in accordance with ITB 13, in separate sealed envelopes, duly marking the envelopes as “Original”, “Alternative” and “Copy.” These envelopes containing the original and the copies shall then be enclosed in one single envelope. |
|  | The inner and outer envelopes shall: (a) bear the name and address of the Bidder; (b) be addressed to the Employer as provided in the BDS pursuant to ITB 22.1; (c) bear the specific identification of this bidding process specified in accordance with BDS 1.1; and (d) bear a warning not to open before the time and date for bid opening. |
|  | If all envelopes are not sealed and marked as required, the Employer will assume no responsibility for the misplacement or premature opening of the bid. |
| Deadline for Submission of Bids | Bids must be received by the Employer at the address and no later than the date and time specified in the BDS. When so specified in the BDS, bidders shall have the option of submitting their bids electronically. Bidders submitting bids electronically shall follow the electronic bid submission procedures specified in the BDS. |
|  | The Employer may, at its discretion, extend the deadline for the submission of bids by amending the Bidding Document in accordance with ITB 8, in which case all rights and obligations of the Employer and Bidders previously subject to the deadline shall thereafter be subject to the deadline as extended. |
| Late Bids | The Employer shall not consider any bid that arrives after the deadline for submission of bids, in accordance with ITB 22. Any bid received by the Employer after the deadline for submission of bids shall be declared late, rejected, and returned unopened to the Bidder. |
| Withdrawal, Substitution, and Modification of Bids | A Bidder may withdraw, substitute, or modify its bid after it has been submitted by sending a written notice, duly signed by an authorized representative, and shall include a copy of the authorization in accordance with ITB 20.2, (except that withdrawal notices do not require copies). The corresponding substitution or modification of the bid must accompany the respective written notice. All notices must be: (a) prepared and submitted in accordance with ITB 20 and ITB 21 (except that withdrawal notices do not require copies), and in addition, the respective envelopes shall be clearly marked “Withdrawal,” “Substitution,” “Modification;” and (b) received by the Employer prior to the deadline prescribed for submission of bids, in accordance with ITB 22. |
|  | Bids requested to be withdrawn in accordance with ITB 24.1 shall be returned unopened to the Bidders. |
|  | No bid may be withdrawn, substituted, or modified in the interval between the deadline for submission of bids and the expiration of the period of bid validity specified by the Bidder on the Letter of Bid or any extension thereof. |
| Bid Opening | Except in the cases specified in ITB 23 and 24, the Employer shall publicly open and read out in accordance with ITB 25.3 all bids received by the deadline, at the date, time and place specified in the BDS, in the presence of Bidders` designated representatives and anyone who choose to attend. Any specific electronic bid opening procedures required if electronic bidding is permitted in accordance with ITB 22.1, shall be as specified in the BDS. |
|  | First, envelopes marked “Withdrawal” shall be opened and read out and the envelope with the corresponding bid shall not be opened, but returned to the Bidder. No bid withdrawal shall be permitted unless the corresponding withdrawal notice contains a valid authorization to request the withdrawal and is read out at bid opening. Next, envelopes marked “Substitution” shall be opened and read out and exchanged with the corresponding bid being substituted, and the substituted bid shall not be opened, but returned to the Bidder. No bid substitution shall be permitted unless the corresponding substitution notice contains a valid authorization to request the substitution and is read out at bid opening. Envelopes marked “Modification” shall be opened and read out with the corresponding bid. No bid modification shall be permitted unless the corresponding modification notice contains a valid authorization to request the modification and is read out at bid opening. Only envelopes that are opened and read out at bid opening shall be considered further. |
|  | All other envelopes shall be opened one at a time, reading out: the name of the Bidder and whether there is a modification; the total Bid Price, including any alternative bids; the presence or absence of a bid security, or Bid Securing Declaration, if required; and any other details as the Employer may consider appropriate. Only alternative bids read out at bid opening shall be considered for evaluation. The Letter of Bid and the Bill of Quantities are to be initialed by representatives of the Employer attending bid opening in the manner specified in the BDS. The Employer shall neither discuss the merits of any bid nor reject any bid (except for late bids, in accordance with ITB 23.1). |
|  | The Employer shall prepare a record of the bid opening that shall include, as a minimum: the name of the Bidder and whether there is a withdrawal, substitution, or modification; the Bid Price, including any alternative bids; and the presence or absence of a bid security, if one was required. The Bidders’ representatives who are present shall be requested to sign the record. The omission of a Bidder’s signature on the record shall not invalidate the contents and effect of the record. A copy of the record shall be distributed to all Bidders. |
| Evaluation and Comparison of Bids |
| Confidentiality | Information relating to the evaluation of bids and recommendation of contract award, shall not be disclosed to Bidders or any other persons not officially concerned with the bidding process until information on Contract award is communicated to all Bidders in accordance with ITB 40. |
|  | Any attempt by a Bidder to influence the Employer in the evaluation of the bids or Contract award decisions may result in the rejection of its bid. |
|  | Notwithstanding ITB 26.2, from the time of bid opening to the time of Contract award, if a Bidder wishes to contact the Employer on any matter related to the bidding process, it shall do so in writing. |
| Clarification of Bids | To assist in the examination, evaluation, and comparison of the bids, and qualification of the Bidders, the Employer may, at its discretion, ask any Bidder for a clarification of its bid given a reasonable time for a response. Any clarification submitted by a Bidder that is not in response to a request by the Employer shall not be considered. The Employer’s request for clarification and the response shall be in writing. No change, including any voluntary increase or decrease in the prices or substance of the bid shall be sought, offered, or permitted, except to confirm the correction of arithmetic errors discovered by the Employer in the evaluation of the bids, in accordance with ITB 31. |
|  | If a Bidder does not provide clarifications of its bid by the date and time set in the Employer’s request for clarification, its bid may be rejected. |
| Deviations, Reservations, and Omissions | During the evaluation of bids, the following definitions apply: (a) “Deviation” is a departure from the requirements specified in the Bidding Document; (b) “Reservation” is the setting of limiting conditions or withholding from complete acceptance of the requirements specified in the Bidding Document; and (c) “Omission” is the failure to submit part or all of the information or documentation required in the Bidding Document. |
| Determination of Responsiveness | The Employer’s determination of a bid’s responsiveness is to be based on the contents of the bid itself, as defined in ITB11. |
|  | A substantially responsive bid is one that meets the requirements of the Bidding Document without material deviation, reservation, or omission. A material deviation, reservation, or omission is one that, (a) if accepted, would: (i) affect in any substantial way the scope, quality, or performance of the Works specified in the Contract; or (ii) limit in any substantial way, inconsistent with the Bidding Document, the Employer’s rights or the Bidder’s obligations under the proposed Contract; or (b) if rectified, would unfairly affect the competitive position of other Bidders presenting substantially responsive bids. |
|  | The Employer shall examine the technical aspects of the bid submitted in accordance with ITB 16, Technical Proposal, in particular, to confirm that all requirements of Section VI (Works Requirements) have been met without any material deviation, reservation or omission. |
|  | If a bid is not substantially responsive to the requirements of the Bidding Document, it shall be rejected by the Employer and may not subsequently be made responsive by correction of the material deviation, reservation, or omission. |
| Nonconformities, Errors, and Omissions | Provided that a bid is substantially responsive, the Employer may waive any nonconformities in the bid. |
|  | Provided that a bid is substantially responsive, the Employer may request that the Bidder submit the necessary information or documentation, within a reasonable period of time, to rectify nonmaterial nonconformities in the bid related to documentation requirements. Requesting information or documentation on such nonconformities shall not be related to any aspect of the price of the Bid. Failure of the Bidder to comply with the request may result in the rejection of its Bid. |
|  | Provided that a bid is substantially responsive, the Employer shall rectify quantifiable nonmaterial nonconformities related to the Bid Price. To this effect, the Bid Price may be adjusted, for comparison purposes only, to reflect the price of a missing or non-conforming item or component. The adjustment shall be made using the methods specified in Section III (Evaluation and Qualification Criteria). |
| Correction of Arithmetical Errors | Provided that the bid is substantially responsive, the Employer shall correct arithmetical errors on the following basis: (a) only for unit price contracts, if there is a discrepancy between the unit price and the total price that is obtained by multiplying the unit price and quantity, the unit price shall prevail and the total price shall be corrected, unless in the opinion of the Employer there is an obvious misplacement of the decimal point in the unit price, in which case the total price as quoted shall govern and the unit price shall be corrected; (b) if there is an error in a total corresponding to the addition or subtraction of subtotals, the subtotals shall prevail and the total shall be corrected; and (c) if there is a discrepancy between words and figures, the amount in words shall prevail, unless the amount expressed in words is related to an arithmetic error, in which case the amount in figures shall prevail subject to (a) and (b) above. |
|  | Bidders shall be requested to accept correction of arithmetical errors. Failure to accept the correction in accordance with ITB 31.1, shall result in the rejection of the Bid. |
| Conversion to Single Currency | For evaluation and comparison purposes, the Employer shall convert all bid prices expressed in amounts in various currencies into an amount in a single currency specified in the BDS, using the selling exchange rates established by the source and on the date specified in the BDS.. |
| Margin of Preference | A margin of preference for domestic bidders shall not apply. |
| Subcontractors | Unless otherwise stated in the BDS, the Employer does not intend to execute any specific elements of the Works by sub-contractors selected in advance by the Employer. The Employer may permit subcontracting for certain specialized works as indicated in Section III. When subcontracting is permitted by the Employer, the specialized sub-contractor’s experience shall be considered for evaluation. Section III describes the qualification criteria for sub-contractors. Bidders may propose subcontracting up to the percentage of total value of contracts or the volume of works as specified in the BDS. |
| Evaluation of Bids | The Employer shall use the criteria and methodologies listed in this Clause. No other evaluation criteria or methodologies shall be permitted. |
|  | To evaluate a bid, the Employer shall consider the following: (a) the bid price, excluding Provisional Sums and the provision, if any, for contingencies in the Summary Bill of Quantities for admeasurement contracts or Schedule of Prices for lump sum contracts, but including Daywork items, where priced competitively; (b) price adjustment for correction of arithmetic errors in accordance with ITB 31.1; (c) converting the amount resulting from applying (a) to (b) above, if relevant, to a single currency in accordance with ITB 32; (d) price adjustment for nonconformities in accordance with ITB 30.3; (e) the additional evaluation factors are specified in Section III (Evaluation and Qualification Criteria); |
|  | The estimated effect of the price adjustment provisions of the Conditions of Contract, applied over the period of execution of the Contract, shall not be taken into account in bid evaluation. |
|  | If the bid for an admeasurement contract, which results in the lowest Evaluated Bid Price, is seriously unbalanced, front loaded or substantially below updated estimates in the opinion of the Employer, the Employer may require the Bidder to produce detailed price analyses for any or all items of the Bill of Quantities, to demonstrate the internal consistency of those prices with the construction methods and schedule proposed. After evaluation of the price analyses, taking into consideration the schedule of estimated Contract payments, the Employer may require that the amount of the performance security be increased at the expense of the Bidder to a level sufficient to protect the Employer against financial loss in the event of default of the successful Bidder under the Contract. |
| Comparison of Bids | The Employer shall compare the evaluated prices of substantially responsive bids established in accordance with ITB 35.2 to determine the lowest evaluated bid. The Employer may however limit the remaining evaluation to the three lowest priced substantially responsive bids, after correction of arithmetical errors as per clause 31.1, if any, and conversion to a single currency as per clause 32.1, if applicable. |
| Qualification of the Bidder | The Employer shall determine to its satisfaction whether the Bidder that is selected as having submitted the lowest evaluated and substantially responsive bid meets the qualifying criteria specified in Section III (Evaluation and Qualification Criteria). |
|  | The determination shall be based upon an examination of the documentary evidence of the Bidder’s qualifications submitted by the Bidder, pursuant to ITB 17.1. |
|  | An affirmative determination of qualification shall be a prerequisite for award of the Contract to the Bidder. A negative determination shall result in disqualification of the bid, in which event the Employer shall proceed to the next lowest evaluated bid to make a similar determination of that Bidder’s qualifications to perform satisfactorily. |
| Employer’s Right to Accept Any Bid, and to Reject Any or All Bids | The Employer reserves the right to accept or reject any bid, and to annul the bidding process and reject all bids at any time prior to contract award, without thereby incurring any liability to Bidders. In case of annulment, all bids submitted and specifically, bid securities, shall be promptly returned to the Bidders. |
| Award of Contract |
| Award Criteria | Subject to ITB 37.1, the Employer shall award the Contract to the Bidder whose bid has been determined to be the lowest evaluated bid and is substantially responsive to the Bidding Document, provided further that the Bidder has been determined to be qualified to perform the Contract satisfactorily. |
| Notification of Award | Prior to the expiration of the period of bid validity, the Employer shall notify the successful Bidder, in writing, via the Letter of Acceptance included in the Contract Forms, that its bid has been accepted. At the same time, the Employer shall also notify all other Bidders of the results of the bidding, and shall publish on the SRTF website , in UNDB online and dgMarket the results identifying the bid (contract) number and the following information: (i) name of each Bidder who submitted a Bid; (ii) bid prices as read out at Bid Opening; (iii) name of the winning Bidder, and the Price it offered, as well as the duration and summary scope of the contract awarded. |
|  | Until a formal contract is prepared and executed, the notification of award shall constitute a binding Contract. |
|  | The Employer shall promptly respond in writing to any unsuccessful Bidder who, after notification of award in accordance with ITB 40.1, requests in writing the grounds on which its bid was not selected. |
| Signing of Contract | Promptly upon notification, the Employer shall send the successful Bidder the Contract Agreement. |
|  | Within twenty-eight (28) days of receipt of the Contract Agreement, the successful Bidder shall sign, date, and return it to the Employer. |
| Performance Security | Within twenty-eight (28) days of the receipt of notification of award from the Employer, the successful Bidder shall furnish the performance security in accordance with the conditions of contract, subject to ITB 35.5, using for that purpose the Performance Security Form included in Section IX (Contract Forms), or another form acceptable to the Employer A foreign institution providing a bond shall have a correspondent financial institution located in the Employer’s Country. For the time being Turkey is considered to be the Employer’s Country. |
|  | Failure of the successful Bidder to submit the above-mentioned Performance Security or to sign the Contract Agreement shall constitute sufficient grounds for the annulment of the award and forfeiture of the bid security. In that event the Employer may award the Contract to the next lowest evaluated Bidder whose offer is substantially responsive and is determined by the Employer to be qualified to perform the Contract satisfactorily. |
| Adjudicator | The Employer proposes the person named in the BDS to be appointed as Adjudicator under the Contract, at the hourly fee specified in the BDS, plus reimbursable expenses. If the Bidder disagrees with this proposal, the Bidder should so state in his Bid. If, in the Letter of Acceptance, the Employer does not agree on the appointment of the Adjudicator, the Employer will request the Appointing Authority designated in the Particular Conditions of Contract (PCC) pursuant to Clause 23.1 of the General Conditions of Contract (GCC), to appoint the Adjudicator. |

Section II - Bid Data Sheet (BDS)

A.  Introduction

| ITB 1.1 | The number of the Invitation for Bids is : [insert number of the Invitation for Bids] The Employer is: [insert the name of the Implementing Entity, as indicated in the Financing Agreement of the Project, in cases when SRTF Yönetim Hizmetleri A. Ş., Turkey conducts the procurement process on behalf of the Implementing Entity, mention this and state ”At any rate the Employer is responsible and liable for the Employer’s obligations in the execution of any resulting contract” . Incases, where the receiving organization differs from the Implementing Entity insert below the name of the receiving organization (beneficiary)] The receiving organization is: [insert the name of the receiving organization ] |
| --- | --- |
| ITB 1.1 | The name of the bidding process is: [insert complete name] The identification number of the bidding process is: [insert identification number] |
| ITB 2.1 | The name of the Project is: [insert name of the Project] |
| ITB 2.1 | Financing Agreement amount: [insert amount] |

B.  Bidding Documents

| ITB 7.1 | For clarification purposes only, the Employer’s address is: Attention: [insert full name of person, if applicable] Street Address: [insert street address and number] Floor/Room number: [insert floor and room number, if applicable] City: [insert name of city or town] Postal Code: [insert postal code, if applicable] Country: [insert name of country] Telephone: : [insert telephone number, including country and city codes] Facsimile number: [insert phone number, with country and city codes] Electronic mail address: [insert email address, if applicable] Requests for clarification should be received by the Employer no later than: [insert no. of days]. |
| --- | --- |
| ITB 7.1 | Web page: www.srtfund.org [insert web page address] |
| ITB 7.4 | A Pre-Bid meeting [insert “shall” or “shall not”] take place. If a Pre-Bid meeting will take place, it will be at the following date, time and place: [insert date, time & place below, if applicable] Time: Place: A site visit conducted by the Employer [insert “shall be” or “shall not be”] organized. |

C.  Preparation of Bids

| ITB 10.1 | The language of the bid is: English [insert language] [Note: In addition to the above language, and if agreed with the SRTF, the Implementing Entity has the option to issue translated versions of the bidding documents in the Arabic language In such case, the following text shall be added:] “In addition, the bidding documents are translated into the Arabic language. Bidders shall have the option to submit their bid in any one of the languages stated above. Bidders shall not submit Bids in more than one language.]” All correspondence exchange shall be in English language. Language for translation of supporting documents and printed literature is English |
| --- | --- |
| ITB 11.1 (b) | The following schedules shall be submitted with the bid: [insert schedules that must be submitted with the Bid, including the priced Bill of Quantities for admeasurement contracts and Schedule of Prices for lump sum contracts] |
| ITB 11.1 (h) | The Bidder shall submit with its bid the following additional documents: [insert type of any additional documents not already listed in ITB 11.1 that must be submitted with the Bid]. |
| ITB 13.1 | Alternative bids [insert “shall be” or “shall not be”] permitted. [Note: For standard non-complex construction it is advised not to allow alternative bids.] |
| ITB 13.2 | Alternative times for completion [insert “shall be” or “shall not be”] permitted. If alternative times for completion are permitted, the evaluation method will be as specified in Section III (Evaluation and Qualification Criteria). [Note: For standard construction it is advised not to allow alternative times.] |
| ITB 13.4 | Alternative technical solutions shall be permitted for the following parts of the Works: [insert parts of the Works] If alternative technical solutions are permitted, the evaluation method will be as specified in Section III (Evaluation and Qualification Criteria). [Note: For standard construction it is advised not to allow alternative technical solutions.] |
| ITB 14.5 | The prices quoted by the Bidder shall not be subject to adjustment during the performance of the Contract |
| ITB 15.1 | The prices shall be quoted by the bidder in: EUR A Bidder expecting to incur expenditures in other currencies for inputs to the Works supplied from outside the Employer’s country and wishing to be paid accordingly, shall indicate up to three currencies of their choice expressed as a percentage of the bid price, together with the exchange rates used in the calculations in the appropriate form(s) included in Section IV. Bidding Forms. |
| ITB 18.1 | The bid validity period shall be: [insert the number of days ] days. [Note: For standard tenders 90 days is enough] |
| ITB 19.1 | A Bid Security shall be required. If however for reasons not related to the Bidder a Bid Security cannot be provided by a Syrian bidder, a Bid Securing Declaration will be considered, provided the Bidder states the reasons as part of his Bid. If a Bid Security shall be required, the amount and currency of the bid security shall be: [ insert amount and currency of the bid security. ] |
| ITB 19.3 (d) | Other types of acceptable securities: None |
| ITB 19.9 | [The following provision should be included and the required corresponding information inserted only if a bid security is not required under provision ITB 19.1 and the Employer wishes to declare the Bidder ineligible for a period of time should the Bidder incur in the actions mentioned in provision ITB 19.9. Otherwise omit.] If the Bidder, who submits a Bid Securing Declaration as per Clause ITB 19.1,incurs any of the actions prescribed in subparagraphs (a) or (b) of this provision, the SRTF will declare the Bidder ineligible to be awarded contracts under SRTF financing for a period of ______ [insert period of time] years. |
| ITB 20.1 | In addition to the original of the bid, the number of copies is: [insert number of copies required]. |
| ITB 20.2 | The written confirmation of authorization to sign on behalf of the Bidder shall consist of:[insert the name and description of the documentation required to demonstrate the authority of the signatory to sign the bid]. |

D.  Submission and Opening of Bids

| ITB 22.1 | Bidders [insert “shall” or “shall not”] have the option of submitting their bids electronically. If electronic bid submission is permitted in accordance with ITB 22.1, the specific bid opening procedures shall be: [insert description of the procedures.] |
| --- | --- |
| ITB 22.1 | For bid submission purposes only, the Employer’s address is: [insert all required and applicable information] Attention: Street Address: Floor/Room number: City: Postal Code: Country: The deadline for bid submission is: Date: Time: Bidders [insert “shall” or “shall not”] have the option of submitting their bids electronically. [The following provision should be included and the required corresponding information inserted only if Bidders have the option of submitting their bids electronically. Otherwise omit.] If bidders have the option of submitting their bids electronically, the electronic bidding submission procedures shall be: [insert a description of the electronic bidding submission procedures] |
| ITB 25.1 | The bid opening shall take place at: [insert all required and applicable information] Street Address: Floor/Room number: City: Country: Date: Time: |
| ITB 25.3 | The Letter of Bid and Priced Bill of Quantities shall be initialled by _________representatives of the Employer conducting Bid opening: _______________________________________________________ |

E.  Evaluation and Comparison of Bids

| ITB 32.1 | The currency that shall be used for bid evaluation and comparison purposes to convert all bid prices expressed in various currencies into a single currency is: EUR The source of exchange rate shall be: [ insert the name of the source: advised: the European Central Bank] The date for the selling exchange rate shall be: two weeks prior to the last deadline for submission of the bids |
| --- | --- |
| ITB 34.3 | a) Contractor’s proposed subcontracting: Maximum percentage of subcontracting permitted is: _______% of the total contract amount or _______% of the volume of work_____________. b) Bidders planning to subcontract more than 10% of total volume of work shall specify, in the Letter of Bid, the activity (ies) or parts of the works to be subcontracted along with complete details of the sub-contractors and their qualification and experience. The qualification and experience of the sub-contractors must meet the minimum criteria for the relevant work to be sub-contracted failing which such sub-contractors will not be permitted to participate. c) Sub-contractors’ qualification and experience will not be considered for evaluation of the Bidder. The Bidder on its own (without taking into account the qualification and experience of the sub-contractor) should meet the qualification criteria. |

F.  Award of Contract

| ITB 43.1 | The Adjudicator proposed by the Employer is:_________________[insert name and address of proposed Adjudicator]. The hourly fee for this proposed Adjudicator shall be:__________[insert amount and currency]. The biographical data of the proposed Adjudicator is as follows: ___________________________________________________________ [provide relevant information, such as education, experience, age, nationality, and present position; attach additional pages as necessary] |
| --- | --- |

Section III - Evaluation and Qualification Criteria

This section contains all the criteria that the Employer shall use to evaluate bids and qualify Bidders if the bidding was not preceded by a prequalification exercise and postqualification is applied. In accordance with ITB 35 and ITB 37, no other methods, criteria and factors shall be used. The Bidder shall provide all the information requested in the forms included in Section 4 (Bidding Forms).

Wherever a Bidder is required to state a monetary amount, Bidders should indicate the EUR equivalent using the rate of exchange determined as follows:

- -For construction turnover or financial data required for each year - Exchange rate prevailing on the last day of the respective calendar year (in which the amounts for that year is to be converted) was originally established.

- -Value of single contract - Exchange rate prevailing on the date of the contract.

Exchange rates shall be taken according to the publicly available source identified in the ITB 32.1. Any error in determining the exchange rates in the Bid may be corrected by the Employer

## Table of Criteria

1. 	Margin of Preference	1-41

2.	Evaluation	1-41

2.1	Adequacy of Technical Proposal	1-41

2.2	Multiple Contracts	1-42

2.3	Alternative Completion Times	1-44

2.4	Technical Alternatives	1-44

2.5 Specialized Subcontractors

3.	Qualification	46

3.1	Eligibility	58

3.2	Historical Contract Non Performance	58

3.3	Financial Situation	58

3.4	Experience	58

3.5	Personnel	58

3.6	Equipment	58

2.	Evaluation

In addition to the criteria listed in ITB 35.2 (a) – (e) the following criteria shall apply:

2.1	Adequacy of Technical Proposal

# Evaluation of the Bidder's Technical Proposal will include an assessment of the Bidder's technical capacity to mobilize key equipment and personnel for the contract consistent with its proposal regarding work methods, scheduling, and material sourcing in sufficient detail and fully in accordance with the requirements stipulated in Section VI (Works Requirements).

2.3	Alternative Completion Times

# An alternative Completion Time, if permitted under ITB 13.2, will be evaluated as follows:

2.4	Technical Alternatives

# Technical alternatives, if permitted under ITB 13.4, will be evaluated as follows:--------

3.	Qualification

| Eligibility and Qualification Criteria | Compliance Requirements | Documentation |
| --- | --- | --- |
| No. | Subject | Requirement | Single Entity | Joint Venture (existing or intended) | Submission Requirements |
|  |  |  |  | All Parties Combined | Each Member | One Member |  |
| 1. Eligibility |
| 1.1 | Nationality | Nationality in accordance with ITB 4.1 | Must meet requirement | Must meet requirement | Must meet requirement | N/A | Forms ELI – 1.1 and 1.2, with attachments |
| 1.1 | Conflict of Interest | No conflicts of interest in accordance with ITB 4.3 (ii) | Must meet requirement | Must meet requirement | Must meet requirement | N/A | Letter of Bid |
| 1.24 | Government Owned Entity | Meets conditions of ITB 4.3 (iv)5 | Must meet requirement | Must meet requirement | Must meet requirement | N/A | Letter of Bid |
| 1.3 | Sanctions or legal barring from procurement process | Meets conditions of ITB 4.3 (i), (ii) Donors supporting the SRTF or the country of the contracting agency on the grounds of previous violations of regulation on fraud and corruption; if the bidder is legally barred from the procurement process in Syria, the exclusion shall only be considered, if it is officially recognized by the National Coalition | Must meet requirement | Must meet requirement | Must meet requirement | N/A | Forms ELI – 1.1 and 1.2, with attachments |
| 1.4 | Financing terrorism | Meets conditions of ITB 4.4 | Must meet requirement | Must meet requirement | Must meet requirement | N/A | Letter of Bid |
| 2. Historical Contract Non-Performance |
| 2.1 | History of Non-Performing Contracts | Non-performance of a contract did not occur as a result of contractor default since 1st January [Insert year]. | Must meet requirement12 | Must meet requirements | Must meet requirement | N/A | Form CON-2 |
| 2.2 | Suspension Based on Execution of Bid Securing Declaration by the Employer or withdrawal of the Bid within Bid validity | Meets conditions of ITB 4.5, i.e. Not under suspension based on execution of a Bid Securing Declaration pursuant to ITB 19.9 under any previous SRTF bidding process.. | Must meet requirement | Must meet requirement | Must meet requirement | N/A | Letter of Bid |
| 2.4 | Litigation History | No consistent history of court/arbitral award decisions against the Bidder since 1st January [insert year] | Must meet requirement | Must meet requirement | Must meet requirement | N/A | Form CON – 2 |
| 3. Financial Situation and Performance |
| 3.1 | Financial Capabilities | The Bidder shall demonstrate that for the latest year the accounts have been closed the working capital is positive. The audited balance sheets or, if not required by the laws of the Bidder’s country, other financial statements acceptable to the Employer, for the last 2_years shall be submitted. | Must meet requirement | Must meet Requirement | N/A | N/A | Form FIN – 3.1, with attachments |
| 3.2 | Average Annual Turnover | Minimum average annual turnover of Euro …………… for the last five years. [Please keep this amount relatively low not to discriminate Syrian companies that have been relatively inactive in the last years] | Must meet requirement | Must meet requirement | Must meet ________%, ___________of the requirement [Please keep this amount relatively low not to discriminate Syrian companies that have been relatively inactive in the last years] | Must meet __________%, ___________of the requirement [Please keep this amount relatively low not to discriminate Syrian companies that have been relatively inactive in the last years] | Form FIN – 3.1 |
| 4. Experience |
| 4.1 (a) | General Construction Experience | Experience under construction contracts in the role of prime contractor, JV member, sub-contractor, or management contractor for at least the last ________years, starting 1st January _____. | Must meet requirement | N/A | Must meet requirement | N/A | Form EXP – 4.1 |
| 4.2 (a) | Specific Construction & Contract Management Experience | (i) A minimum number of At least three similar contracts have been completed (taking over certificate) as a prime contractor, joint venture member, management contractor or sub-contractor19 in the last five years ending on the deadline for submission of the bids. | Must meet requirement | Must meet requirement | N/A | N/A | Form EXP 4.2(a) |

5	Personnel

The Bidder must demonstrate that it will have the personnel for the key positions that meet the following requirements:

| No. | Position | Total Work Similar Experience (years) | In Similar Works Experience (years) |
| --- | --- | --- | --- |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| 4 |  |  |  |
| 5 |  |  |  |

The Bidder shall provide details of the proposed personnel and their experience records in the relevant Forms included in Section IV, Bidding Forms.

6.	Equipment

The Bidder must demonstrate that it will have access to the key Contractor’s equipment listed hereafter:

| No. | Equipment Type and Characteristics | Minimum Number required |
| --- | --- | --- |
| 1 |  |  |
| 2 |  |  |
| 3 |  |  |
| 4 |  |  |
| 5 |  |  |

The Bidder shall provide further details of proposed items of equipment using the relevant Form in Section IV.

Section IV - Bidding Forms

Table of Forms

Letter of Bid	60

Schedules	63

Bill of Quantities	63

Schedule(s) of Adjustment Data	67

Form of Bid Security (Bank Guarantee)	68

Form of Bid Security (Bid Bond)	70

Form of Bid-Securing Declaration	71

Technical Proposal	72

Technical Proposal Forms	72

Forms for Personnel	73

Forms for Equipment	75

Bidder’s Qualification	76

Bidder Information Form	77

Information Form for JV Bidders	78

Historical Contract Non-Performance, Pending Litigation and Litigation History	79

Current Contract Commitments / Works in Progress	80

Financial Situation and Performance	81

Average Annual Construction Turnover	83

Financial Resources	84

General Construction Experience	85

Specific Construction and Contract Management Experience	86

Construction Experience in Key Activities	88

Letter of Bid

The Bidder must prepare the Letter of Bid on stationery with its letterhead clearly showing the Bidder’s complete name and address. Note: All italicized text is for use in preparing these form and shall be deleted from the final products.

Date: [insert date (as day, month and year) of Bid Submission]

ICB No.: [insert number of bidding process]

Invitation for Bid No.: [insert identification]

Alternative No.: [insert identification No if this is a Bid for an alternative]

To:  [insert complete name of Employer]

- We have examined and have no reservations to the Bidding Documents, including Addenda issued in accordance with Instructions to Bidders (ITB 8)	;

- We meet the eligibility requirements and have no conflict of interest in accordance with ITB 4 and we confirm that none of the other reasons for exclusion in accordance with ITB Sub-Clauses 4.2 and 4.3 apply to our firm, its affiliates or subsidiaries—including any subcontractors or suppliers for any part of the contract;

- We have not been suspended nor declared ineligible by SRTF based on execution of a Bid Securing Declaration in the Employer’s country in accordance with ITB 4.4

- We offer to execute in conformity with the Bidding Documents the following Works: [insert a brief description of the Works];

- The total price of our Bid is:

[insert the total price of the bid in words and figures, indicating the various amounts and the respective currencies];

- Our bid shall be valid for a period of [specify the number of calendar days as per ITB 18.1]  days from the date fixed for the bid submission deadline in accordance with the Bidding Documents, and it shall remain binding upon us and may be accepted at any time before the expiration of that period;

- If our bid is accepted, we commit to obtain a performance security in accordance with the Bidding Documents;

- We are not participating, as a Bidder or as a subcontractor, in more than one bid in this bidding process in accordance with ITB 4.2(e), other than alternative bids submitted in accordance with ITB 13;

- We confirm that none of the other reasons for exclusion in accordance with ITB Sub-Clauses 4.2, 4.3 and 4.4 apply to our firm, its affiliates or subsidiaries, including any subcontractors or suppliers for any part of the contract ;

- We have paid, or will pay the following commissions, gratuities, or fees with respect to the bidding process or execution of the Contract: [insert complete name of each Recipient, its full address, the reason for which each commission or gratuity  was paid and the amount and currency of each such commission or gratuity]

| Name of Recipient | Address | Reason | Amount |
| --- | --- | --- | --- |

(If none has been paid or is to be paid, indicate “none.”)

- We understand that this bid, together with your written acceptance thereof included in your notification of award, shall constitute a binding contract between us, until a formal contract is prepared and executed; and

- We understand that you are not bound to accept the lowest evaluated bid or any other bid that you may receive.

- We hereby certify that we have taken steps to ensure that no person acting for us or on our behalf will engage in any type of fraud and corruption

Name of the Bidder*	[insert complete name of person signing the Bid]

Name of the person duly authorized to sign the Bid on behalf of the Bidder** [insert complete name of person duly authorized to sign the Bid]

Title of the person signing the Bid [insert complete title of the person signing the Bid]

Signature of the person named above	 [insert signature of person whose name and capacity are shown above]

Date signed _[insert date of signing] day of [insert month], [insert year]

*: In the case of the Bid submitted by joint venture specify the name of the Joint Venture as Bidder

**: Person signing the Bid shall have the power of attorney given by the Bidder to be attached with the Bid Schedules.

Schedules

Bill of Quantities

Objectives

The objectives of the Bill of Quantities are:

(a)	to provide sufficient information on the quantities of Works to be performed to enable bids to be prepared efficiently and accurately; and

(b)	when a Contract has been entered into, to provide a priced Bill of Quantities for use in the periodic valuation of Works executed.

In order to attain these objectives, Works should be itemized in the Bill of Quantities in sufficient detail to distinguish between the different classes of Works, or between Works of the same nature carried out in different locations or in other circumstances which may give rise to different considerations of cost.  Consistent with these requirements, the layout and contents of the Bill of Quantities should be as simple and brief as possible.

Daywork Schedule

A Daywork Schedule should be included only if the probability of unforeseen work, outside the items included in the Bill of Quantities, is extremely high and if the Employer is very experienced in the management of works contracts, including its appointed evaluation committee. In case of works with a value lower than 5 MEURO, Daywork schedule is better to be omitted.  To facilitate checking by the Employer of the realism of rates quoted by the bidders, the Daywork Schedule should normally comprise the following:

(a)	A list of the various classes of labor, materials, and Constructional Plant for which basic daywork rates or prices are to be inserted by the Bidder, together with a statement of the conditions under which the Contractor shall be paid for work executed on a daywork basis.

(b)	Nominal quantities for each item of daywork, to be priced by each Bidder at daywork rates as Bid.  The rate to be entered by the Bidder against each basic daywork item should include the Contractor’s profit, overheads, supervision, and other charges.

Provisional Sums

A general provision for physical contingencies (quantity overruns) may be made by including a provisional sum in the Summary Bill of Quantities.  Where such provisional sumis used, the Special Conditions of Contract should state the manner in which it shall be used, and under whose authority (usually the Project Manager’s).

The estimated cost of specialized work to be carried out, or of special goods to be supplied, by other contractors should be indicated in the relevant part of the Bill of Quantities as a particular provisional sum with an appropriate brief description.  A separate procurement procedure is normally carried out by the Employer to select such specialized contractors.  To provide an element of competition among the bidders in respect of any facilities, amenities, attendance, etc., to be provided by the successful Bidder as prime Contractor for the use and convenience of the specialist contractors, each related provisional sum should be followed by an item in the Bill of Quantities inviting the Bidder to quote a sum for such amenities, facilities, attendance, etc.

These Notes for Preparing a Bill of Quantities are intended only as information for the Employer or the person drafting the Bidding Documents.  They should not be included in the final documents.

1. Sample Bill of Quantities

(EUR instead of local currency and other Foreign Currency)

| Item no. | Description | Unit | Quantity | Rate | Amount |
| --- | --- | --- | --- | --- | --- |
|  | Contingency 10% |  |  |  |  |
| Total |  |

Sample Activity Schedule

| Item no. | Description | Unit | Amount |
| --- | --- | --- | --- |

2. Schedule of Payment Currencies

For ...........................insert name of Section of the Works

Separate tables may be required if the various sections of the Works (or of the Bill of Quantities) will have substantially different currency requirements.  The Employer should insert the names of each Section of the Works.

|  | A | B | C | D |
| --- | --- | --- | --- | --- |
| Name of Payment Currency | Amount of Currency | Rate of Exchange to EUR | EUR Equivalent C = A x B | Percentage of Total Bid Price (TBP) 100xC TBP |
| EUR ( instead of local currency) |  | 1.00 |  |  |
| Currency #2 |  |  |  |  |
| Currency #3 |  |  |  |  |
| Total Bid Price |  |  |  | 100.00 |
| Provisional Sums Expressed in EUR |  | 1.00 |  |  |
| TOTAL BID PRICE (Including provisional sum) |  |  |  |  |

Form of Bid Security (Bank Guarantee)

[Guarantor letterhead or SWIFT identifier code]

Beneficiary:

[Insert name and address of the Employer]

Invitation for Bids No: _[Insert reference number for the Invitation for Bids]

Date:  [Insert date of issue]

BID GUARANTEE No.: [Insert guarantee reference number]

Guarantor:  _[Insert name and address of place of issue, unless indicated in the letterhead]

We have been informed that [insert name of the Bidder, which in the case of a joint venture shall be the name of the joint venture (whether legally constituted or prospective) or the names of all members thereof] (hereinafter called "the Applicant") has submitted or will submit to the Beneficiary its bid (hereinafter called "the Bid") for the execution of [insert description of contract] under Invitation for Bids No. [insert number] (“the IFB”).

Furthermore, we understand that, according to the Beneficiary’s conditions, bids must be supported by a bid guarantee.

At the request of the Applicant, we , as Guarantor, hereby irrevocably undertake to pay the Beneficiary any sum or sums not exceeding in total an amount of [insert amount in letters] (insert amount in numbers) upon receipt by us of the Beneficiary’s complying supported by the Beneficiary’s statement, whether in the demand itself or a separate signed document accompanying or identifying the demand, stating either that the Applicant:

(a) 	has withdrawn its Bid during the period of bid validity specified by the Applicant in the Letter of Bid, or any extension thereto provided by the Applicant; or

(b) 	having been notified of the acceptance of its Bid by the Beneficiary during the period of bid validity, (i) fails to execute the Contract Agreement or (ii) fails to furnish the performance security, in accordance with the Instructions to Bidders (“ITB”) of the Beneficiary’s bidding document.

This guarantee will expire: (a) if the Applicant is the successful Bidder, upon our receipt of copies of the contract agreement signed by the Applicant and the performance security issued to the Beneficiary upon the instruction of the Applicant; and (b) if the Applicant is not the successful Bidder, upon the earlier of (i) our receipt of a copy of the Beneficiary’s notification to the Applicant of the results of the bidding process; or (ii) twenty-eight days after the Validity Period, which date shall be established by presentation to us of copies of the Letter of Bid and any extension(s) thereto, accompanied by the bidding document; or (c) three years after the date of issue of this guarantee.

Consequently, any demand for payment under this guarantee must be received by us at the office indicated above on or before that date.

This guarantee is subject to the Uniform Rules for Demand Guarantees (URDG) 2010 Revision, ICC Publication No. 758.

_____________________________

[signature(s)]

Note:  All italicized text is for use in preparing this form and shall be deleted from the final product.

Form of Bid-Securing Declaration

[Only applicable for a Syrian bidder, who cannot arrange a bid security as per ITB19.1]

Date: [insert date (as day, month and year)]

Bid No.: [insert number of bidding process]

Alternative No.: [insert identification No if this is a Bid for an alternative]

To: [insert complete name of Employer]

We, the undersigned, declare that:

We understand that, according to your conditions, our bid must be supported by a Bid-Securing Declaration.

We accept that we will automatically be suspended from being eligible for bidding in any contract financed by SRTF  for the period of time of [insert number of months or years] starting on [insert date], if we are in breach of our obligation(s) under the bid conditions, because we:

(a) 	have withdrawn our Bid during the period of bid validity specified in the Letter of Bid; or

(b) 	having been notified of the acceptance of our Bid by the Employer during the period of bid validity, (i) fail or refuse to execute the Contract, if required, or (ii) fail or refuse to furnish the Performance Security, in accordance with the ITB.

We understand this Bid-Securing Declaration shall expire if we are not the successful Bidder, upon the earlier of (i) our receipt of your notification to us of the name of the successful Bidder; or (ii) twenty-eight days after the expiration of our Bid.

Name of the Bidder*	[insert complete name of person signing the Bid]

Name of the person duly authorized to sign the Bid on behalf of the Bidder** [insert complete name of person duly authorized to sign the Bid]

Title of the person signing the Bid [insert complete title of the person signing the Bid]

Signature of the person named above	 [insert signature of person whose name and capacity are shown above]

Date signed _[insert date of signing] day of [insert month], [insert year]

*: In the case of the Bid submitted by joint venture specify the name of the Joint Venture as Bidder

**: Person signing the Bid shall have the power of attorney given by the Bidder to be attached with the Bid [Note: In case of a Joint Venture, the Bid-Securing Declaration must be in the name of all members to the Joint Venture that submits the bid.]

Technical Proposal

Technical Proposal Forms

Personnel

Equipment

Site Organization

Method Statement

Mobilization Schedule

Construction Schedule

Others

Forms for Personnel

Form PER – 1: Proposed Personnel

Bidders should provide the names of suitably qualified personnel to meet the specified requirements for each of the positions listed in Section III (Evaluation and Qualification Criteria). The data on their experience should be supplied using the Form below for each candidate.

| 1. | Title of position |
| --- | --- |
|  | Name |
| 2. | Title of position |
|  | Name |
| 3. | Title of position |
|  | Name |
| 4. | Title of position |
|  | Name |
| 5. | Title of position |
|  | Name |
| 6. | Title of position |
|  | Name |
| etc. | Title of position |
|  | Name |

Form PER – 2:  Resume of Proposed Personnel

The Bidder shall provide all the information requested below. Fields with asterisk (*) shall be used for evaluation.

| Position* |
| --- |
| Personnel information | Name * | Date of birth |
|  | Professional qualifications |
| Present employment | Name of Employer |
|  | Address of Employer |
|  | Telephone | Contact (manager / personnel officer) |
|  | Fax | E-mail |
|  | Job title | Years with present Employer |

Summarize professional experience in reverse chronological order. Indicate particular technical and managerial experience relevant to the project.

| From* | To* | Company, Project , Position, and Relevant Technical and Management Experience* |
| --- | --- | --- |

Forms for Equipment

The Bidder shall provide adequate information to demonstrate clearly that it has the capability to meet the requirements for the key equipment listed in Section III (Evaluation and Qualification Criteria).   The Bidder shall provide all the information requested below, to the extent possible.

|  | DESCRIPTION (type/make/model) | Power/ capacity | No of units | Age (years) | Owned (O) or hired (H)/ and percentage of ownership | Origin (country) | Present approximate value in euro or national currency |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A) | CONSTRUCTION PLANT |  |  |  |  |  |  |
|  |  |  |  |  | / |  |  |
|  |  |  |  |  | / |  |  |
|  |  |  |  |  | / |  |  |
|  |  |  |  |  | / |  |  |
|  |  |  |  |  | / |  |  |
|  |  |  |  |  | / |  |  |
|  |  |  |  |  | / |  |  |
|  |  |  |  |  | / |  |  |
|  |  |  |  |  | / |  |  |
|  |  |  |  |  | / |  |  |
|  |  |  |  |  | / |  |  |
|  |  |  |  |  | / |  |  |
|  |  |  |  |  | / |  |  |
|  |  |  |  |  | / |  |  |
|  |  |  |  |  | / |  |  |
|  |  |  |  |  | / |  |  |

|  | DESCRIPTION (type/make/model) | Power/ capacity | No of units | Age (years) | Owned (O) or hired (H)/ and percentage of ownership | Origin (country) | Present approximate value in euro or national currency |
| --- | --- | --- | --- | --- | --- | --- | --- |
| B) | VEHICLES AND TRUCKS |  |  |  |  |  |  |
|  |  |  |  |  | / |  |  |
|  |  |  |  |  | / |  |  |
|  |  |  |  |  | / |  |  |
|  |  |  |  |  | / |  |  |
|  |  |  |  |  | / |  |  |
|  |  |  |  |  | / |  |  |
|  |  |  |  |  | / |  |  |
|  |  |  |  |  | / |  |  |
|  |  |  |  |  | / |  |  |
|  |  |  |  |  | / |  |  |
| C) | OTHER PLANT |  |  |  | / |  |  |
|  |  |  |  |  | / |  |  |
|  |  |  |  |  | / |  |  |
|  |  |  |  |  | / |  |  |
|  |  |  |  |  | / |  |  |
|  |  |  |  |  | / |  |  |
|  |  |  |  |  | / |  |  |
|  |  |  |  |  | / |  |  |
|  |  |  |  |  | / |  |  |
|  |  |  |  |  | / |  |  |

Bidder’s Qualification

To establish its qualifications to perform the contract in accordance with Section III (Evaluation and Qualification Criteria) the Bidder shall provide the information requested in the corresponding Information Sheets included hereunder

Form ELI -1.1: Bidder Information Form

Date: _________________
ICB No. and title: _________________
Page __________of _______________pages

Bidder's name

In case of Joint Venture (JV), name of each member:

Bidder's actual or intended country of registration: [indicate country of Constitution]

Bidder's actual or intended year of incorporation:

Bidder's legal address [in country of registration]:

Bidder's authorized representative information Name: _____________________________________ Address: ___________________________________ Telephone/Fax numbers: _______________________ E-mail address: ______________________________

1. Attached are copies of original documents of ( Articles of Incorporation (or equivalent documents of constitution or association), and/or documents of registration of the legal entity named above, in accordance with ITB 4.3. In case of a Syrian bidder, if due to the prevailing situation in the country any such expired document could not be extended/renewed, the Bidder must provide the expired documents and a sworn statement on impossibility of extension/renewal. ( In case of JV, letter of intent to form JV or JV agreement, in accordance with ITB 4.1. 2. Included are the organizational chart, a list of Board of Directors, and the beneficial ownership.

Form ELI -1.2: Information Form for JV Bidders

(to be completed for each member of Joint Venture)

Date: _______________
ICB No. and title: __________________
Page _______________ of ____________ pages

Bidder’s Joint Venture name:

JV member’s name:

JV member’s country of registration:

JV member’s year of constitution:

JV member’s legal address in country of constitution:

JV member’s authorized representative information Name: ____________________________________ Address: __________________________________ Telephone/Fax numbers: _____________________ E-mail address: _____________________________

1. Attached are copies of original documents of ( Articles of Incorporation (or equivalent documents of constitution or association), and/or registration documents of the legal entity named above, in accordance with ITB 4.3. In case of a Syrian bidder, if due to the prevailing situation in the country any such expired document could not be extended/renewed, the Bidder must provide the expired documents and a sworn statement on impossibility of extension/renewal. 2. Included are the organizational chart, a list of Board of Directors, and the beneficial ownership.

Form CON – 2: Historical Contract Non-Performance, Pending Litigation and Litigation History

Bidder’s Name: ________________
Date: ______________________
Joint Venture Member’s Name_________________________
ICB No. and title: ___________________________
Page _______________of ______________pages

| Non-Performed Contracts in accordance with Section III, Evaluation Criteria and Qualifications |
| --- |
| ( Contract non-performance did not occur since 1st January [insert year] specified in Section III, Evaluation Criteria and Qualifications, Sub-Factor 2.1. ( Contract(s) not performed since 1st January [insert year] specified in Section III, Evaluation Criteria and Qualifications, requirement 2.1 |
| Year | Non- performed portion of contract | Contract Identification | Total Contract Amount (current value, currency, exchange rate and US$ equivalent) |
|  |  | Contract Identification: Name of Employer: Address of Employer: Reason(s) for non performance: |  |
| Pending Litigation, in accordance with Section III, Evaluation Criteria and Qualifications |
| ( No pending litigation in accordance with Section III, Evaluation Criteria and Qualifications, Sub-Factor 2.3. |
| ( Pending litigation in accordance with Section III, Evaluation Criteria and Qualifications, Sub-Factor 2.3 as indicated below. |

Form FIN – 3.1: Financial Situation and Performance

Bidder’s Name: ________________
Date: ______________________
Joint Venture Member’s Name_________________________
ICB No. and title: ___________________________
Page _______________of ______________pages

1. Financial data

| Type of Financial information in (currency) | Historic information for previous _________years, ______________ (amount in currency, currency, exchange rate, EUR equivalent) |
| --- | --- |
|  | Year 1 | Year 2 | Year 3 | Year4 | Year 5 |
| Statement of Financial Position (Information from Balance Sheet) |
| Total Assets (TA) |  |  |  |  |  |
| Total Liabilities (TL) |  |  |  |  |  |
| Total Equity/Net Worth (NW) |  |  |  |  |  |
| Current Assets (CA) |  |  |  |  |  |
| Current Liabilities (CL) |  |  |  |  |  |
| Working Capital (WC) |  |  |  |  |  |
| Information from Income Statement |
| Total Revenue (TR) |  |  |  |  |  |
| Profits Before Taxes (PBT) |  |  |  |  |  |

2. Financial documents

The Bidder and its parties shall provide copies of financial statements for two years pursuant Section III, Evaluation and Qualifications Criteria, Sub-factor 3.2. The financial statements shall:

(a) 	reflect the financial situation of the Bidder or in case of JV member , and not an affiliated entity  (such as parent company or group member).

(b)	be independently audited or certified in accordance with local legislation. In case of a Syrian bidder, if due to the prevailing situation in the country the auditing or certification of an annual account for a particular year was impossible, the annual account for such year without auditing or certification may be submitted, along woth a sworn statement in the impossibility of auditing or certification for such year.

(c)	be complete, including all notes to the financial statements.

(d)	correspond to accounting periods already completed and audited.

(	Attached are copies of financial statements  for the ____________years required above; and complying with the requirements

Form EXP - 4.1: General Construction Experience

Bidder’s Name: ________________
Date: ______________________
Joint Venture Member’s Name_________________________
ICB No. and title: ___________________________
Page _______________of ______________pages

| Starting Year | Ending Year | Contract Identification | Role of Bidder |
| --- | --- | --- | --- |
|  |  | Contract name: ____________________ Brief Description of the Works performed by the Bidder: _____________________________ Amount of contract: ___________________ Name of Employer: ____________________ Address: _____________________________ |  |
|  |  | Contract name: _________________________ Brief Description of the Works performed by the Bidder: _____________________________ Amount of contract: ___________________ Name of Employer: ___________________ Address: _________________________ |  |
|  |  | Contract name: ________________________ Brief Description of the Works performed by the Bidder: __________________________ Amount of contract: ___________________ Name of Employer: ___________________ Address: _________________________ |  |

Form EXP - 4.2(a): Specific Construction and Contract Management Experience

Bidder’s Name: ________________
Date: ______________________
Joint Venture Member’s Name_________________________
ICB No. and title: ___________________________
Page _______________of ______________pages

| Similar Contract No. | Information |
| --- | --- |
| Contract Identification |  |
| Award date |  |
| Completion date (taking over/provisional acceptance) |  |
| Role in Contract | Prime Contractor ( | Member in JV ( | Management Contractor ( | Sub-contractor ( |
| Total Contract Amount |  | EUR * |
| If member in a JV or sub-contractor, specify participation in total Contract amount |  |  | * |
| Employer's Name: |  |
| Address: Telephone/fax number E-mail: |  |

Form EXP - 4.2(a) (cont.)

Specific Construction and Contract Management Experience (cont.)

| Similar Contract No. | Information |
| --- | --- |
| Description of the similarity in accordance with Sub-Factor 4.2(a) of Section III: |  |
| 1. Amount |  |
| 2. Physical size of required works items |  |
| 3. Complexity |  |
| 4. Methods/Technology |  |
| 5. Construction rate for key activities |  |
| 6. Other Characteristics |  |

Section V - Eligible Countries

Eligibility for the Provision of Goods, Works and Services in SRTF-Financed Procurement

- In accordance with applicable SRTF Procurement Guidelines  SRTF permits firms and individuals from all countries to offer goods, works and services for SRTF-financed projects. As an exception, firms of a Country or goods manufactured in a Country may be excluded if:

(i) participation of a bidder (or any of its personnel) is ruled out by sanctions issued by the UN Security Council, the EU, the US or any other Donor  government; or

(ii) any import of goods from that Country or any payments to persons or entities in that Country is ruled out by sanctions issued by the UN Security Council, the EU, the US or any other Donor  government; or

(iii) the bidder is legally barred from the procurement process in its own or any Donor country or the country of the contracting agency on the grounds of previous violations of regulation on fraud and corruption; if the bidder is legally barred from the procurement process in Syria, the exclusion shall only be considered, if it is officially recognized by the National Coalition

2.	For the information of bidders with reference to 1 (i) and (ii) above, at the present time SRTF Donors are the following ones:

_________________________

_________________________

PART 2 – Works Requirements

Section VI - Works Requirements

Table of Contents

Specifications	2-4

Drawings	2-6

Supplementary Information	2-7

Specifications

A set of precise and clear Specifications is a prerequisite for bidders to respond realistically and competitively to the requirements of the Employer without qualifying or conditioning their bids.  In the context of international competitive bidding, the Specifications must be drafted to permit the widest possible competition and, at the same time, present a clear statement of the required standards of workmanship, materials, and performance of the goods and services to be procured.  Only if this is done shall the objectives of economy, efficiency, and fairness in procurement be realized, responsiveness of bids be ensured, and the subsequent task of Bid evaluation facilitated.  The Specifications should require that all goods and materials to be incorporated in the Works be new, unused, of the most recent or current models, and incorporate all recent improvements in design and materials unless provided otherwise in the Contract.

Samples of Specifications from previous similar projects in the same country are useful in to prepare Specifications.  The use of metric units is encouraged by the World Bank.  Most Specifications are normally written specially by the Employer or Project Manager to suit the Contract Works in hand.  There is no standard set of Specifications for universal application in all sectors in all countries, but there are established principles and practices, which are reflected in these documents.

There are considerable advantages in standardizing General Specifications for repetitive Works in recognized public sectors, such as highways, ports, railways, urban housing, irrigation, and water supply, in the same country or region where similar conditions prevail. The General Specifications should cover all classes of workmanship, materials, and equipment commonly involved in construction, although not necessarily to be used in a particular Works Contract.  Deletions or addendums should then adapt the General Specifications to apply them to the particular Works.

Care must be taken in drafting Specifications to ensure that they are not restrictive.  In the Specifications of standards for goods, materials, and workmanship, recognized international standards should be used as much as possible.  Where other particular standards are used, whether national standards of the Borrower’s country or other standards, the Specifications should state that goods, materials, and workmanship that meet other authoritative standards, and which ensure substantially equal or higher quality than the standards mentioned, shall also be acceptable. To that effect, the following sample clause may be inserted in the Special Conditions or Specifications.

“Equivalency of Standards and Codes

Wherever reference is made in the Contract to specific standards and codes to be met by the goods and materials to be furnished, and work performed or tested, the provisions of the latest current edition or revision of the relevant standards and codes in effect shall apply, unless otherwise expressly stated in the Contract.  Where such standards and codes are national, or relate to a particular country or region, other authoritative standards that ensure a substantially equal or higher quality than the standards and codes specified shall be accepted subject to the Project Manager’s prior review and written consent.  Differences between the standards specified and the proposed alternative standards shall be fully described in writing by the Contractor and submitted to the Project Manager at least 28 days prior to the date when the Contractor desires the Project Manager’s consent.  In the event the Project Manager determines that such proposed deviations do not ensure substantially equal or higher quality, the Contractor shall comply with the standards specified in the documents.”

These Notes for Preparing Specifications are intended only as information for the Employer or the person drafting the bidding documents.  They should not be included in the final documents.

Drawings

Insert here a list of Drawings.  The actual Drawings, including site plans, should be attached to this section or annexed in a separate folder.

Supplementary Information

PART 3 – Conditions of Contract and Contract Forms

Section VII.  General Conditions of Contract

These General Conditions of Contract (GCC), read in conjunction with the Particular Conditions of Contract (PCC) and other documents listed therein, should be a complete document expressing fairly the rights and obligations of both parties.

These General Conditions of Contract have been developed on the basis of considerable international experience in the drafting and management of contracts, bearing in mind a trend in the construction industry towards simpler, more straightforward language.

The GCC can be used for both smaller admeasurement contracts and lump sum contracts.

## Table of Clauses

A.  General	6

1.	Definitions	6

2.	Interpretation	8

3.	Language and Law	9

4.	Project Manager’s Decisions	9

5.	Delegation	9

6.	Communications	10

7.	Subcontracting	10

8.	Other Contractors	10

9.	Personnel and Equipment	10

10.	Employer’s and Contractor’s Risks	10

11.	Employer’s Risks	10

12.	Contractor’s Risks	11

13.	Insurance	11

14.	Site Data	12

15.	Contractor to Construct the Works	12

16.	The Works to Be Completed by the Intended Completion Date	12

17.	Approval by the Project Manager	12

18.	Safety		13

19.	Discoveries	13

20.	Possession of the Site	13

21.	Access to the Site	13

22.	Instructions, Inspections and Audits	13

23.	Appointment of the Adjudicator	13

24.	Procedure for Disputes	14

25.	Corrupt and Fraudulent Practices	14

B.  Time Control	16

26.	Program	16

27.	Extension of the Intended Completion Date	17

28.	Acceleration	17

29.	Delays Ordered by the Project Manager	17

30.	Management Meetings	17

31.	Early Warning	18

C.  Quality Control	18

32.	Identifying Defects	18

33.	Tests	18

34.	Correction of Defects	18

35.	Uncorrected Defects	19

D.  Cost Control	19

36.	Contract Price	19

37.	Changes in the Contract Price	19

38.	Variations	19

39.	Cash Flow Forecasts	20

40.	Payment Certificates	20

41.	Payments	21

42.	Compensation Events	21

43.	Tax		23

44.	Currencies	23

45.	Price Adjustment	23

46.	Retention	23

47.	Liquidated Damages	23

48.	Bonus		24

49.	Advance Payment	24

50.	Securities	24

51.	Dayworks	24

52.	Cost of Repairs	25

E.  Finishing the Contract	25

53.	Completion	25

54.	Taking Over	25

55.	Final Account	25

56.	Operating and Maintenance Manuals	25

57.	Termination	26

58.	Payment upon Termination	27

59.	Property	27

60.	Release from Performance	27

61.	Suspension of Bank Loan or Credit	27

General Conditions of Contract

A.  General

| Definitions | Boldface type is used to identify defined terms. The Accepted Contract Amount means the amount accepted in the Letter of Acceptance for the execution and completion of the Works and the remedying of any defects. The Activity Schedule is a schedule of the activities comprising the construction, installation, testing, and commissioning of the Works in a lump sum contract. It includes a lump sum price for each activity, which is used for valuations and for assessing the effects of Variations and Compensation Events. The Adjudicator is the person appointed jointly by the Employer and the Contractor to resolve disputes in the first instance, as provided for in GCC 23. SRTF means the Syria Recovery Trust Fund acting through the SRTF Yönetim Hizmetleri A. Ş., Turkey (translated: SRTF Management Services JSC) (Syria A.S.). Bill of Quantities means the priced and completed Bill of Quantities forming part of the Bid. Compensation Events are those defined in GCC Clause 42 hereunder. The Completion Date is the date of completion of the Works as certified by the Project Manager, in accordance with GCC Sub-Clause 53.1. The Contract is the Contract between the Employer and the Contractor to execute, complete, and maintain the Works. It consists of the documents listed in GCC Sub-Clause 2.3 below. The Contractor is the party whose Bid to carry out the Works has been accepted by the Employer. The Contractor’s Bid is the completed bidding document submitted by the Contractor to the Employer. The Contract Price is the Accepted Contract Amount stated in the Letter of Acceptance and thereafter as adjusted in accordance with the Contract. Days are calendar days; months are calendar months. Dayworks are varied work inputs subject to payment on a time basis for the Contractor’s employees and Equipment, in addition to payments for associated Materials and Plant. A Defect is any part of the Works not completed in accordance with the Contract. The Defects Liability Certificate is the certificate issued by Project Manager upon correction of defects by the Contractor. The Defects Liability Period is the period named in the PCC pursuant to Sub-Clause 34.1 and calculated from the Completion Date. Drawings means the drawings of the Works, as included in the Contract, and any additional and modified drawings issued by (or on behalf of) the Employer in accordance with the Contract, include calculations and other information provided or approved by the Project Manager for the execution of the Contract. The Employer is the party who employs the Contractor to carry out the Works, as specified in the PCC. Equipment is the Contractor’s machinery and vehicles brought temporarily to the Site to construct the Works. “In writing” or “written” means hand-written, type-written, printed or electronically made, and resulting in a permanent record; The Initial Contract Price is the Contract Price listed in the Employer’s Letter of Acceptance. The Intended Completion Date is the date on which it is intended that the Contractor shall complete the Works. The Intended Completion Date is specified in the PCC. The Intended Completion Date may be revised only by the Project Manager by issuing an extension of time or an acceleration order. Materials are all supplies, including consumables, used by the Contractor for incorporation in the Works. Plant is any integral part of the Works that shall have a mechanical, electrical, chemical, or biological function. The Project Manager is the person named in the PCC (or any other competent person appointed by the Employer and notified to the Contractor, to act in replacement of the Project Manager) who is responsible for supervising the execution of the Works and administering the Contract. PCC means Particular Conditions of Contract. The Site is the area defined as such in the PCC. Site Investigation Reports are those that were included in the bidding documents and are factual and interpretative reports about the surface and subsurface conditions at the Site. Specification means the Specification of the Works included in the Contract and any modification or addition made or approved by the Project Manager. The Start Date is given in the PCC. It is the latest date when the Contractor shall commence execution of the Works. It does not necessarily coincide with any of the Site Possession Dates. A Subcontractor is a person or corporate body who has a Contract with the Contractor to carry out a part of the work in the Contract, which includes work on the Site. Temporary Works are works designed, constructed, installed, and removed by the Contractor that are needed for construction or installation of the Works. A Variation is an instruction given by the Project Manager which varies the Works. The Works are what the Contract requires the Contractor to construct, install, and turn over to the Employer, as defined in the PCC. |
| --- | --- |
| Interpretation | In interpreting these GCC, words indicating one gender include all genders. Words indicating the singular also include the plural and words indicating the plural also include the singular. Headings have no significance. Words have their normal meaning under the language of the Contract unless specifically defined. The Project Manager shall provide instructions clarifying queries about these GCC. If sectional completion is specified in the PCC, references in the GCC to the Works, the Completion Date, and the Intended Completion Date apply to any Section of the Works (other than references to the Completion Date and Intended Completion Date for the whole of the Works). The documents forming the Contract shall be interpreted in the following order of priority: the Letter of Acceptance the addenda Nos ________(if any) the Particular Conditions the General Conditions of Contract, including appendix; the Contractor’s Bid the Specification the Drawings Bill of Quantities; and any other document listed in the PCC as forming part of the Contract. |
| Language and Law | The language of the Contract and the law governing the Contract are stated in the PCC. Throughout the execution of the Contract, the Contractor shall comply with the import of goods and services prohibitions in the Employer’s country when (a) as a matter of law or official regulations, the SRTF prohibits commercial relations with that country; or (b) by an act of compliance with a decision of the United Nations Security Council taken under Chapter VII of the Charter of the United Nations, the SRTF prohibits any import of goods from that country or any payments to any country, person, or entity in that country. |
| Project Manager’s Decisions | Except where otherwise specifically stated, the Project Manager shall decide contractual matters between the Employer and the Contractor in the role representing the Employer. |
| Delegation | Otherwise specified in the PCC, the Project Manager may delegate any of his duties and responsibilities to other people, except to the Adjudicator, after notifying the Contractor, and may revoke any delegation after notifying the Contractor. |
| Communications | Communications between parties that are referred to in the Conditions shall be effective only when in writing. A notice shall be effective only when it is delivered. |
| Subcontracting | The Contractor may subcontract with the approval of the Project Manager, but may not assign the Contract without the approval of the Employer in writing. Subcontracting shall not alter the Contractor’s obligations. |
| Other Contractors | The Contractor shall cooperate and share the Site with other contractors, public authorities, utilities, and the Employer between the dates given in the Schedule of Other Contractors, as referred to in the PCC. The Contractor shall also provide facilities and services for them as described in the Schedule. The Employer may modify the Schedule of Other Contractors, and shall notify the Contractor of any such modification. |
| Personnel and Equipment | The Contractor shall adhere to minimum social standards ("Core Labour Standards") ratified by Syria and employ the key personnel and use the equipment identified in its Bid, to carry out the Works or other personnel and equipment approved by the Project Manager. The Project Manager shall approve any proposed replacement of key personnel and equipment only if their relevant qualifications or characteristics are substantially equal to or better than those proposed in the Bid. If the Project Manager asks the Contractor to remove a person who is a member of the Contractor’s staff or work force, stating the reasons, the Contractor shall ensure that the person leaves the Site within seven days and has no further connection with the work in the Contract. If the Employer, Project Manager or Contractor determines, that any employee of the Contractor be determined to have engaged in corrupt, fraudulent, collusive, coercive, or obstructive practice during the execution of the Works, then that employee shall be removed in accordance with Clause 9.2 above. |
| Employer’s and Contractor’s Risks | The Employer carries the risks which this Contract states are Employer’s risks, and the Contractor carries the risks which this Contract states are Contractor’s risks. |
| Employer’s Risks | From the Start Date until the Defects Liability Certificate has been issued, the following are Employer’s risks: The risk of personal injury, death, or loss of or damage to property (excluding the Works, Plant, Materials, and Equipment), which are due to use or occupation of the Site by the Works or for the purpose of the Works, which is the unavoidable result of the Works or negligence, breach of statutory duty, or interference with any legal right by the Employer or by any person employed by or contracted to him except the Contractor. The risk of damage to the Works, Plant, Materials, and Equipment to the extent that it is due to a fault of the Employer or in the Employer’s design, or due to war or radioactive contamination directly affecting the country where the Works are to be executed. From the Completion Date until the Defects Liability Certificate has been issued, the risk of loss of or damage to the Works, Plant, and Materials is an Employer’s risk except loss or damage due to a Defect which existed on the Completion Date, an event occurring before the Completion Date, which was not itself an Employer’s risk, or the activities of the Contractor on the Site after the Completion Date. |
| Contractor’s Risks | 12.1 From the Starting Date until the Defects Liability Certificate has been issued, the risks of personal injury, death, and loss of or damage to property (including, without limitation, the Works, Plant, Materials, and Equipment) which are not Employer’s risks are Contractor’s risks. |
| Insurance | The Contractor shall provide, in the joint names of the Employer and the Contractor, insurance cover from the Start Date to the end of the Defects Liability Period, in the amounts and deductibles stated in the PCC for the following events which are due to the Contractor’s risks: loss of or damage to the Works, Plant, and Materials; loss of or damage to Equipment; loss of or damage to property (except the Works, Plant, Materials, and Equipment) in connection with the Contract; and personal injury or death. Policies and certificates for insurance shall be delivered by the Contractor to the Project Manager for the Project Manager’s approval before the Start Date. All such insurance shall provide for compensation to be payable in the types and proportions of currencies required to rectify the loss or damage incurred. If the Contractor does not provide any of the policies and certificates required, the Employer may effect the insurance which the Contractor should have provided and recover the premiums the Employer has paid from payments otherwise due to the Contractor or, if no payment is due, the payment of the premiums shall be a debt due. Alterations to the terms of an insurance shall not be made without the approval of the Project Manager. Both parties shall comply with any conditions of the insurance policies. |
| Site Data | The Contractor shall be deemed to have examined any Site Data referred to in the PCC, supplemented by any information available to the Contractor. |
| Contractor to Construct the Works | The Contractor shall construct and install the Works in accordance with the Specifications and Drawings. |
| The Works to Be Completed by the Intended Completion Date | The Contractor may commence execution of the Works on the Start Date and shall carry out the Works in accordance with the Program submitted by the Contractor, as updated with the approval of the Project Manager, and complete them by the Intended Completion Date. |
| Approval by the Project Manager | The Contractor shall submit Specifications and Drawings showing the proposed Temporary Works to the Project Manager, for his approval. The Contractor shall be responsible for design of Temporary Works. The Project Manager’s approval shall not alter the Contractor’s responsibility for design of the Temporary Works. The Contractor shall obtain approval of third parties to the design of the Temporary Works, where required. All Drawings prepared by the Contractor for the execution of the temporary or permanent Works, are subject to prior approval by the Project Manager before this use. |
| Safety | The Contractor shall be responsible for the safety of all activities on the Site. |
| Discoveries | Anything of historical or other interest or of significant value unexpectedly discovered on the Site shall be the property of the Employer. The Contractor shall notify the Project Manager of such discoveries and carry out the Project Manager’s instructions for dealing with them. |
| Possession of the Site | The Employer shall give possession of all parts of the Site to the Contractor. If possession of a part is not given by the date stated in the PCC, the Employer shall be deemed to have delayed the start of the relevant activities, and this shall be a Compensation Event. |
| Access to the Site | The Contractor shall allow the Project Manager and any person authorized by the Project Manager access to the Site and to any place where work in connection with the Contract is being carried out or is intended to be carried out. |
| Instructions, Inspections and Audits | The Contractor shall carry out all instructions of the Project Manager which comply with the applicable laws where the Site is located. The Contractor shall keep, and shall make all reasonable efforts to cause its Subcontractors and subconsultants to keep, accurate and systematic accounts and records in respect of the Works in such form and details as will clearly identify relevant time changes and costs. The Contractor shall permit and shall cause its Subcontractors and subconsultants to permit, SRTF and/or persons appointed by SRTF to inspect the Site and/or the accounts and records relating to the performance of the Contract and the submission of the bid, and to have such accounts and records audited by auditors appointed by SRTF if requested by SRTF. The Contractor’s and its Subcontractors’ and subconsultants’ attention is drawn to Sub-Clause 25.1 which provides, inter alia, that acts intended to materially impede the exercise of SRTF’s inspection and audit rights provided for under Sub-Clause 22.2 constitute a prohibited practice subject to contract termination(as well as to a determination of ineligibility pursuant to the SRTF’s prevailing sanctions procedures). |
| Appointment of the Adjudicator | The Adjudicator shall be appointed jointly by the Employer and the Contractor, at the time of the Employer’s issuance of the Letter of Acceptance. If, in the Letter of Acceptance, the Employer does not agree on the appointment of the Adjudicator, the Employer will request the Appointing Authority designated in the PCC, to appoint the Adjudicator within 14 days of receipt of such request. Should the Adjudicator resign or die, or should the Employer and the Contractor agree that the Adjudicator is not functioning in accordance with the provisions of the Contract, a new Adjudicator shall be jointly appointed by the Employer and the Contractor. In case of disagreement between the Employer and the Contractor, within 30 days, the Adjudicator shall be designated by the Appointing Authority designated in the PCC at the request of either party, within 14 days of receipt of such request. |
| Procedure for Disputes | If the Contractor believes that a decision taken by the Project Manager was either outside the authority given to the Project Manager by the Contract or that the decision was wrongly taken, the decision shall be referred to the Adjudicator within 14 days of the notification of the Project Manager’s decision. The Adjudicator shall give a decision in writing within 28 days of receipt of a notification of a dispute. The Adjudicator shall be paid by the hour at the rate specified in the PCC, together with reimbursable expenses of the types specified in the PCC, and the cost shall be divided equally between the Employer and the Contractor, whatever decision is reached by the Adjudicator. Either party may refer a decision of the Adjudicator to an Arbitrator within 28 days of the Adjudicator’s written decision. If neither party refers the dispute to arbitration within the above 28 days, the Adjudicator’s decision shall be final and binding. The arbitration shall be conducted in accordance with the arbitration procedures published by the institution named and in the place specified in the PCC. |
| Corrupt and Fraudulent Practices, Financing Terrorism | It is SRTF’s policy to require that Recipients, as well as bidders, suppliers, and contractors and their agents (whether declared or not), personnel, subcontractors, sub-consultants, service providers and suppliers under SRTF-financed contracts, observe the highest standard of ethics during the procurement and execution of such contracts. In pursuance of this policy, SRTF: (a) defines, for the purposes of this provision, the terms set forth below as follows: (i) “corrupt practice” is the offering, giving, receiving or soliciting, directly or indirectly, of anything of value to influence improperly the actions of another party; (ii) “fraudulent practice” is any act or omission, including a misrepresentation, that knowingly or recklessly misleads, or attempts to mislead, a party to obtain a financial or other benefit or to avoid an obligation; (iii) “collusive practice” is an arrangement between two or more parties designed to achieve an improper purpose, including to influence improperly the actions of another party; (iv) “coercive practice” is impairing or harming, or threatening to impair or harm, directly or indirectly, any party or the property of the party to influence improperly the actions of a party; (v) “obstructive practice” is (aa) deliberately destroying, falsifying, altering or concealing of evidence material to the investigation or making false statements to investigators in order to materially impede a SRTF investigation into allegations of a corrupt, fraudulent, coercive or collusive practice; and/or threatening, harassing or intimidating any party to prevent it from disclosing its knowledge of matters relevant to the investigation or from pursuing the investigation; or (bb) acts intended to materially impede the exercise of SRTF’s inspection and audit rights provided for under sub-clause 3.1 (e) below. (b) will reject a proposal for award if it determines that the bidder recommended for award has, directly or through an agent, engaged in corrupt, fraudulent, collusive, coercive or obstructive practices in competing for the contract in question; (c) will cancel the portion of the financial support allocated to a contract if it determines at any time that representatives of the Recipient of the financial support engaged in corrupt, fraudulent, collusive, or coercive practices during the procurement or the execution of that contract, without the Recipient having taken timely and appropriate action satisfactory to SRTF to address such practices when they occur. The Employer requires the Contractor to disclose any commissions or fees that may have been paid or are to be paid to agents or any other party with respect to the bidding process or execution of the Contract. The information disclosed must include at least the name and address of the agent or other party, the amount and currency, and the purpose of the commission, gratuity or fee. The Contractor and its Subcontractors may not be engaged in financing terrorism, including providing financing or support to any persons who are designated by the U.S. Department of Treasury as “Specially Designated Nationals” or subject to sanctions by the EU. |

B.  Time Control

| Program | Within the time stated in the PCC, after the date of the Letter of Acceptance, the Contractor shall submit to the Project Manager for approval a Program showing the general methods, arrangements, order, and timing for all the activities in the Works. In the case of a lump sum contract, the activities in the Program shall be consistent with those in the Activity Schedule. An update of the Program shall be a program showing the actual progress achieved on each activity and the effect of the progress achieved on the timing of the remaining work, including any changes to the sequence of the activities. The Contractor shall submit to the Project Manager for approval an updated Program at intervals no longer than the period stated in the PCC. If the Contractor does not submit an updated Program within this period, the Project Manager may withhold the amount stated in the PCC from the next payment certificate and continue to withhold this amount until the next payment after the date on which the overdue Program has been submitted. In the case of a lump sum contract, the Contractor shall provide an updated Activity Schedule within 14 days of being instructed to by the Project Manager. The Project Manager’s approval of the Program shall not alter the Contractor’s obligations. The Contractor may revise the Program and submit it to the Project Manager again at any time. A revised Program shall show the effect of Variations and Compensation Events. |
| --- | --- |
| Extension of the Intended Completion Date | The Project Manager shall extend the Intended Completion Date if a Compensation Event occurs or a Variation is issued which makes it impossible for Completion to be achieved by the Intended Completion Date without the Contractor taking steps to accelerate the remaining work, which would cause the Contractor to incur additional cost. The Project Manager shall decide whether and by how much to extend the Intended Completion Date within 21 days of the Contractor asking the Project Manager for a decision upon the effect of a Compensation Event or Variation and submitting full supporting information. If the Contractor has failed to give early warning of a delay or has failed to cooperate in dealing with a delay, the delay by this failure shall not be considered in assessing the new Intended Completion Date. |
| Acceleration | When the Employer wants the Contractor to finish before the Intended Completion Date, the Project Manager shall obtain priced proposals for achieving the necessary acceleration from the Contractor. If the Employer accepts these proposals, the Intended Completion Date shall be adjusted accordingly and confirmed by both the Employer and the Contractor. If the Contractor’s priced proposals for an acceleration are accepted by the Employer, they are incorporated in the Contract Price and treated as a Variation. |
| Delays Ordered by the Project Manager | The Project Manager may instruct the Contractor to delay the start or progress of any activity within the Works. |
| Management Meetings | Either the Project Manager or the Contractor may require the other to attend a management meeting. The business of a management meeting shall be to review the plans for remaining work and to deal with matters raised in accordance with the early warning procedure. The Project Manager shall record the business of management meetings and provide copies of the record to those attending the meeting and to the Employer. The responsibility of the parties for actions to be taken shall be decided by the Project Manager either at the management meeting or after the management meeting and stated in writing to all who attended the meeting. |
| Early Warning | The Contractor shall warn the Project Manager at the earliest opportunity of specific likely future events or circumstances that may adversely affect the quality of the work, increase the Contract Price, or delay the execution of the Works. The Project Manager may require the Contractor to provide an estimate of the expected effect of the future event or circumstance on the Contract Price and Completion Date. The estimate shall be provided by the Contractor as soon as reasonably possible. The Contractor shall cooperate with the Project Manager in making and considering proposals for how the effect of such an event or circumstance can be avoided or reduced by anyone involved in the work and in carrying out any resulting instruction of the Project Manager. |

C.  Quality Control

| Identifying Defects | The Project Manager shall check the Contractor’s work and notify the Contractor of any Defects that are found. Such checking shall not affect the Contractor’s responsibilities. The Project Manager may instruct the Contractor to search for a Defect and to uncover and test any work that the Project Manager considers may have a Defect. |
| --- | --- |
| Tests | If the Project Manager instructs the Contractor to carry out a test not specified in the Specification to check whether any work has a Defect and the test shows that it does, the Contractor shall pay for the test and any samples. If there is no Defect, the test shall be a Compensation Event. |
| Correction of Defects | The Project Manager shall give notice to the Contractor of any Defects before the end of the Defects Liability Period, which begins at Completion, and is defined in the PCC. The Defects Liability Period shall be extended for as long as Defects remain to be corrected. Every time notice of a Defect is given, the Contractor shall correct the notified Defect within the length of time specified by the Project Manager’s notice. |
| Uncorrected Defects | If the Contractor has not corrected a Defect within the time specified in the Project Manager’s notice, the Project Manager shall assess the cost of having the Defect corrected, and the Contractor shall pay this amount. |

D.  Cost Control

| Contract Price | The Bill of Quantities shall contain priced items for the Works to be performed by the Contractor. The Bill of Quantities is used to calculate the Contract Price. The Contractor will be paid for the quantity of the work accomplished at the rate in the Bill of Quantities for each item. |
| --- | --- |
| Changes in the Contract Price | If the final quantity of the work done differs from the quantity in the Bill of Quantities for the particular item by more than 25 percent, provided the change exceeds 1 percent of the Initial Contract Price, the Project Manager shall adjust the rate to allow for the change. The Project Manager shall not adjust rates from changes in quantities if thereby the Initial Contract Price is exceeded by more than 15 percent, except with the prior approval of the Employer. If requested by the Project Manager, the Contractor shall provide the Project Manager with a detailed cost breakdown of any rate in the Bill of Quantities. |
| Variations | All Variations shall be included in updated Programs produced by the Contractor. The Contractor shall provide the Project Manager with a quotation for carrying out the Variation when requested to do so by the Project Manager. The Project Manager shall assess the quotation, which shall be given within seven (7) days of the request or within any longer period stated by the Project Manager and before the Variation is ordered. If the Contractor’s quotation is unreasonable, the Project Manager may order the Variation and make a change to the Contract Price, which shall be based on the Project Manager’s own forecast of the effects of the Variation on the Contractor’s costs. If the Project Manager decides that the urgency of varying the work would prevent a quotation being given and considered without delaying the work, no quotation shall be given and the Variation shall be treated as a Compensation Event. The Contractor shall not be entitled to additional payment for costs that could have been avoided by giving early warning. If the work in the Variation corresponds to an item description in the Bill of Quantities and if, in the opinion of the Project Manager, the quantity of work above the limit stated in Sub-Clause 39.1 or the timing of its execution do not cause the cost per unit of quantity to change, the rate in the Bill of Quantities shall be used to calculate the value of the Variation. If the cost per unit of quantity changes, or if the nature or timing of the work in the Variation does not correspond with items in the Bill of Quantities, the quotation by the Contractor shall be in the form of new rates for the relevant items of work. |
| Cash Flow Forecasts | When the Program, is updated, the Contractor shall provide the Project Manager with an updated cash flow forecast. The cash flow forecast shall include different currencies, as defined in the Contract, converted as necessary using the Contract exchange rates. |
| Payment Certificates | The Contractor shall submit to the Project Manager monthly statements of the estimated value of the work executed less the cumulative amount certified previously. The Project Manager shall check the Contractor’s monthly statement and certify the amount to be paid to the Contractor. The value of work executed shall be determined by the Project Manager. The value of work executed shall comprise the value of the quantities of work in the Bill of Quantities that have been completed. The value of work executed shall include the valuation of Variations and Compensation Events. The Project Manager may exclude any item certified in a previous certificate or reduce the proportion of any item previously certified in any certificate in the light of later information. |
| Payments | Payments shall be adjusted for deductions for advance payments and retention. The Employer shall pay the Contractor the amounts certified by the Project Manager within 28 days of the date of each certificate. If the Employer makes a late payment, the Contractor shall be paid interest on the late payment in the next payment. Interest shall be calculated from the date by which the payment should have been made up to the date when the late payment is made at the prevailing rate of interest for commercial borrowing for each of the currencies in which payments are made. If an amount certified is increased in a later certificate or as a result of an award by the Adjudicator or an Arbitrator, the Contractor shall be paid interest upon the delayed payment as set out in this clause. Interest shall be calculated from the date upon which the increased amount would have been certified in the absence of dispute. Unless otherwise stated, all payments and deductions shall be paid or charged in the proportions of currencies comprising the Contract Price. Items of the Works for which no rate or price has been entered in shall not be paid for by the Employer and shall be deemed covered by other rates and prices in the Contract. |
| Compensation Events | The following shall be Compensation Events: The Employer does not give access to a part of the Site by the Site Possession Date pursuant to GCC Sub-Clause 20.1. The Employer modifies the Schedule of Other Contractors in a way that affects the work of the Contractor under the Contract. The Project Manager orders a delay or does not issue Drawings, Specifications, or instructions required for execution of the Works on time. The Project Manager instructs the Contractor to uncover or to carry out additional tests upon work, which is then found to have no Defects. The Project Manager unreasonably does not approve a subcontract to be let. Ground conditions are substantially more adverse than could reasonably have been assumed before issuance of the Letter of Acceptance from the information issued to bidders (including the Site Investigation Reports), from information available publicly and from a visual inspection of the Site. The Project Manager gives an instruction for dealing with an unforeseen condition, caused by the Employer, or additional work required for safety or other reasons. Other contractors, public authorities, utilities, or the Employer does not work within the dates and other constraints stated in the Contract, and they cause delay or extra cost to the Contractor. The advance payment is delayed. The effects on the Contractor of any of the Employer’s Risks. The Project Manager unreasonably delays issuing a Certificate of Completion. If a Compensation Event would cause additional cost or would prevent the work being completed before the Intended Completion Date, the Contract Price shall be increased and/or the Intended Completion Date shall be extended. The Project Manager shall decide whether and by how much the Contract Price shall be increased and whether and by how much the Intended Completion Date shall be extended. As soon as information demonstrating the effect of each Compensation Event upon the Contractor’s forecast cost has been provided by the Contractor, it shall be assessed by the Project Manager, and the Contract Price shall be adjusted accordingly. If the Contractor’s forecast is deemed unreasonable, the Project Manager shall adjust the Contract Price based on the Project Manager’s own forecast. The Project Manager shall assume that the Contractor shall react competently and promptly to the event. The Contractor shall not be entitled to compensation to the extent that the Employer’s interests are adversely affected by the Contractor’s not having given early warning or not having cooperated with the Project Manager. |
| Tax | Tax payable by the Contractor is included in the Contract Price. |
| Currencies | Where payments are made in currencies other than EUR, the exchange rates used for calculating the amounts to be paid shall be the exchange rates stated in the Contractor’s Bid. |
| Price Adjustment | Prices shall not be adjusted for fluctuations in the cost of inputs. |
| Retention | The Employer shall retain from each payment due to the Contractor the proportion stated in the PCC until Completion of the whole of the Works. Upon the issue of a Certificate of Completion of the Works by the Project Manager, in accordance with GCC 51.1, half the total amount retained shall be repaid to the Contractor and half when the Defects Liability Period has passed and the Project Manager has certified that all Defects notified by the Project Manager to the Contractor before the end of this period have been corrected. The Contractor may substitute retention money with an “on demand” Bank guarantee. |
| Liquidated Damages | The Contractor shall pay liquidated damages to the Employer at the rate per day stated in the PCC for each day that the Completion Date is later than the Intended Completion Date. The total amount of liquidated damages shall not exceed the amount defined in the PCC. The Employer may deduct liquidated damages from payments due to the Contractor. Payment of liquidated damages shall not affect the Contractor’s liabilities. If the Intended Completion Date is extended after liquidated damages have been paid, the Project Manager shall correct any overpayment of liquidated damages by the Contractor by adjusting the next payment certificate. The Contractor shall be paid interest on the overpayment, calculated from the date of payment to the date of repayment, at the rates specified in GCC Sub-Clause 41.1. |
| Bonus | The Contractor shall be paid a Bonus calculated at the rate per calendar day stated in the PCC for each day (less any days for which the Contractor is paid for acceleration) that the Completion is earlier than the Intended Completion Date. The Project Manager shall certify that the Works are complete, although they may not be due to be complete. If no rate is stipulated under clause 48.1 of the PCC, no bonus is envisaged for this contract. |
| Advance Payment | The Employer shall make advance payment to the Contractor of the amounts stated in the PCC by the date stated in the PCC, against provision by the Contractor of an Unconditional Bank Guarantee in a form and by a bank acceptable to the Employer in amounts and currencies equal to the advance payment. The Guarantee shall remain effective until the advance payment has been repaid, but the amount of the Guarantee shall be progressively reduced by the amounts repaid by the Contractor. Interest shall not be charged on the advance payment. The Contractor is to use the advance payment only to pay for Equipment, Plant, Materials, and mobilization expenses required specifically for execution of the Contract. The Contractor shall demonstrate that advance payment has been used in this way by supplying copies of invoices or other documents to the Project Manager. The advance payment shall be repaid by deducting proportionate amounts from payments otherwise due to the Contractor, following the schedule of completed percentages of the Works on a payment basis. No account shall be taken of the advance payment or its repayment in assessing valuations of work done, Variations, price adjustments, Compensation Events, Bonuses, or Liquidated Damages. |
| Securities | The Performance Security shall be provided to the Employer no later than the date specified in the Letter of Acceptance and shall be issued in an amount specified in the PCC, by a bank acceptable to the Employer, and denominated in the types and proportions of the currencies in which the Contract Price is payable. The Performance Security shall be valid until a date 28 days from the date of issue of the Certificate of Completion in the case of a Bank Guarantee. |
| Dayworks | If applicable, the Dayworks rates in the Contractor’s Bid shall be used only when the Project Manager has given written instructions in advance for additional work to be paid for in that way. All work to be paid for as Dayworks shall be recorded by the Contractor on forms approved by the Project Manager. Each completed form shall be verified and signed by the Project Manager within two days of the work being done. The Contractor shall be paid for Dayworks subject to obtaining signed Dayworks forms. |
| Cost of Repairs | Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Correction periods shall be remedied by the Contractor at the Contractor’s cost if the loss or damage arises from the Contractor’s acts or omissions. |

E.  Finishing the Contract

| Completion | The Contractor shall request the Project Manager to issue a Certificate of Completion of the Works, and the Project Manager shall do so upon deciding that the whole of the Works is completed. |
| --- | --- |
| Taking Over | The Employer shall take over the Site and the Works within seven days of the Project Manager’s issuing a certificate of Completion. |
| Final Account | The Contractor shall supply the Project Manager with a detailed account of the total amount that the Contractor considers payable under the Contract before the end of the Defects Liability Period. A draft final account shall be supplied by the Contractor to the Project manager before the certificate of completion is issued The Project Manager shall issue a Defects Liability Certificate and certify any final payment that is due to the Contractor within 56 days of receiving the Contractor’s account if it is correct and complete. If it is not, the Project Manager shall issue within 56 days a schedule that states the scope of the corrections or additions that are necessary. If the Final Account is still unsatisfactory after it has been resubmitted, the Project Manager shall decide on the amount payable to the Contractor and issue a payment certificate. |
| Operating and Maintenance Manuals | If “as built” Drawings and/or operating and maintenance manuals are required, the Contractor shall supply them by the dates stated in the PCC. If the Contractor does not supply the Drawings and/or manuals by the dates stated in the PCC pursuant to GCC Sub-Clause 56.1, or they do not receive the Project Manager’s approval, the Project Manager shall withhold the amount stated in the PCC from payments due to the Contractor. |
| Termination | The Employer or the Contractor may terminate the Contract if the other party causes a fundamental breach of the Contract. Fundamental breaches of Contract shall include, but shall not be limited to, the following: the Contractor stops work for 28 days when no stoppage of work is shown on the current Program and the stoppage has not been authorized by the Project Manager; the Project Manager instructs the Contractor to delay the progress of the Works, and the instruction is not withdrawn within 28 days; the Employer or the Contractor is made bankrupt or goes into liquidation other than for a reconstruction or amalgamation; a payment certified by the Project Manager is not paid by the Employer to the Contractor within 84 days of the date of the Project Manager’s certificate; the Project Manager gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within a reasonable period of time determined by the Project Manager; the Contractor does not maintain a Security, which is required; the Contractor has delayed the completion of the Works by the number of days for which the maximum amount of liquidated damages can be paid, as defined in the PCC; or if the Contractor, in the judgment of the Employer or of the SRTF, has engaged in corrupt, fraudulent, collusive, coercive or obstructive practices, in competing for or in executing the Contract, then the Client may, after giving fourteen (14) days written notice to the Contractor, terminate the Contract and expel him from the Site. When either party to the Contract gives notice of a breach of Contract to the Project Manager for a cause other than those listed under GCC Sub-Clause 56.2 above, the Project Manager shall decide whether the breach is fundamental or not. Notwithstanding the above, the Employer may terminate the Contract for convenience. If the Contract is terminated, the Contractor shall stop work immediately, make the Site safe and secure, and leave the Site as soon as reasonably possible. |
| Payment upon Termination | If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Project Manager shall issue a certificate for the value of the work done and Materials ordered less advance payments received up to the date of the issue of the certificate and less the percentage to apply to the value of the work not completed, as specified in the PCC. Additional Liquidated Damages shall not apply. If the total amount due to the Employer exceeds any payment due to the Contractor, the difference shall be a debt payable to the Employer. If the Contract is terminated for the Employer’s convenience or because of a fundamental breach of Contract by the Employer, the Project Manager shall issue a certificate for the value of the work done, Materials ordered, the reasonable cost of removal of Equipment, repatriation of the Contractor’s personnel employed solely on the Works, and the Contractor’s costs of protecting and securing the Works, and less advance payments received up to the date of the certificate. |
| Property | All Materials on the Site, Plant, Equipment, Temporary Works, and Works shall be deemed to be the property of the Employer if the Contract is terminated because of the Contractor’s default. |
| Release from Performance | If the Contract is frustrated by the outbreak of war or by any other event entirely outside the control of either the Employer or the Contractor, the Project Manager shall certify that the Contract has been frustrated. The Contractor shall make the Site safe and stop work as quickly as possible after receiving this certificate and shall be paid for all work carried out before receiving it and for any work carried out afterwards to which a commitment was made. |
| Suspension of SRTF Financing | In the event that SRTF suspends the Financing to the Employer, from which part of the payments to the Contractor are being made: The Employer is obligated to notify the Contractor of such suspension within 7 days of having received SRTF’s suspension notice. If the Contractor has not received sums due it within the 28 days for payment provided for in Sub-Clause 40.1, the Contractor may immediately issue a 14-day termination notice. |

Section VIII.  Particular Conditions of Contract

Except where otherwise specified, all PCC should be filled in by the Employer prior to issuance of the Bidding Documents.  Schedules and reports to be provided by the Employer should be annexed.

| A. General |
| --- |
| GCC 1.1 (s) | The Employer is [insert name, address, and name of authorized representative]. [Add if applicable] Also in case Syria A.S. signs the Contract on behalf of and in the name of the Employer, the Employer is responsible and liable for the Employer’s obligations in the execution of the Contract. |
| GCC 1.1 (v) | The Intended Completion Date for the whole of the Works shall be [insert date] [If different dates are specified for completion of the Works by section (“sectional completion” or milestones), these dates should be listed here] |
| GCC 1.1 (y) | The Project Manager is [insert name, address, and name of authorized representative]. |
| GCC 1.1 (aa) | The Site is located at [insert address of Site ] and is defined in drawings No. [insert numbers] |
| GCC 1.1 (dd) | The Start Date shall be [insert date]. |
| GCC 1.1 (hh) | The Works consist of [insert brief summary, including relationship to other contracts under the Project]. |
| GCC 2.2 | Sectional Completions are: [insert nature and dates, if appropriate] |
| GCC 2.3(i) | The following documents also form part of the Contract: [list documents] |
| GCC 3.1 | The language of the contract is [insert name of the language. Standard: English; exceptionally Arabic with approval of Syria A.S.The language shall be that of the bid]. The law that applies to the Contract is the law of [insert name of Country Germany with place of performance Gaziantep]. |
| GCC 5.1 | The Project manager [may or may not] delegate any of his duties and responsibilities. |
| GCC 8.1 | Schedule of other contractors: [insert Schedule of Other Contractors, if appropriate] |
| GCC 13.1 | The minimum insurance amounts and deductibles shall be: (a) for loss or damage to the Works, Plant and Materials: [insert amounts]. (b) For loss or damage to Equipment: [insert amounts]. (c) for loss or damage to property (except the Works, Plant, Materials, and Equipment) in connection with Contract [insert amounts]. (d) for personal injury or death: of the Contractor’s employees: [amount]. of other people: [amount]. If due to reasons not related to the Contractor, a Syrian Contractor cannot arrange insurance as stated above, the Contractor shall submit a declaration to the Employer, that he shall be fully responsible for events otherwise to be covered under insurance. |
| GCC 14.1 | Site Data are: [list Site Data] |
| GCC 20.1 | The Site Possession Date(s) shall be: [insert location(s) and date(s)] |
| GCC 23.1 & GCC 23.2 | Appointing Authority for the Adjudicator: [insert name of Authority]. |
| GCC 24.3 | Hourly rate and types of reimbursable expenses to be paid to the Adjudicator: [insert hourly fees and reimbursable expenses]. |
| GCC 24.4 | “Rules of Conciliation and Arbitration of the International Chamber of Commerce (ICC): All disputes arising in connection with the present Contract shall be finally settled under the Rules of Conciliation and Arbitration of the International Chamber of Commerce by one or more arbitrators appointed in accordance with said Rules.” |
| B. Time Control |
| GCC 26.1 | The Contractor shall submit for approval a Program for the Works within [number] days from the date of the Letter of Acceptance. |
| GCC 26.3 | The period between Program updates is [insert number] days. The amount to be withheld for late submission of an updated Program is [insert amount]. |
| C. Quality Control |
| GCC 34.1 | The Defects Liability Period is: [insert number] days. [The Defects Liability Period is usually limited to 12 months, but could be less in very simple cases] |
| D. Cost Control |
| GCC 41.1 | Payments shall be made through direct payment from Syria A.S. or KfW as SRTF Trustee to a bank account designated by the Contractor. For a Syrian contractor, exceptionally payment may be made in cash, but only if this is demonstrably unavoidable to the satisfaction of Syria A.S. due to reasons not related to the Supplier. |
| GCC 46.1 | The proportion of payments retained is: [insert percentage] [The retention amount is usually 10 percent.] |
| GCC 47.1 | The liquidated damages for the whole of the Works are [insert percentage of the final Contract Price] per day. The maximum amount of liquidated damages for the whole of the Works is [insert percentage] of the final Contract Price. [Usually liquidated damages are set between 0.05 percent and 0.10 percent per day, and the total amount is not to exceed between 5 percent and 10 percent of the Contract Price. If Sectional Completion and Damages per Section have been agreed, the latter should be specified here] |
| GCC 48.1 | The Bonus for the whole of the Works is [insert percentage of final Contract Price] per day. The maximum amount of Bonus for the whole of the Works is [insert percentage] of the final Contract Price. [If early completion would provide benefits to the Employer, this clause should remain; otherwise delete. The Bonus is usually numerically equal to the liquidated damages.] |
| GCC 49.1 | The Advance Payments shall be 10% of the Contract price, i.e.: [insert amount(s)] and shall be paid to the Contractor no later than [insert date(s)]. |
| GCC 50.1 | The Performance Security amount is 10% of the Contract price, i.e.[insert amount(s) denominated in the types and proportions of the currencies in which the Contract Price is payable, or in a freely convertible currency acceptable to the Employer] The Performance Security shall be in the form of a Bank Guarantee as per the format provided in Section IX of the bidding documents. [A Bank Guarantee shall be unconditional (on demand) (see Section IX, Contract Forms). An amount of10 percent of the Contract Price is specified for Performance Bank Guarantees. ] |
| E. Finishing the Contract |
| GCC 56.1 | The date by which operating and maintenance manuals are required is [insert date]. The date by which “as built” drawings are required is [insert date]. |
| GCC 56.2 | The amount to be withheld for failing to produce “as built” drawings and/or operating and maintenance manuals by the date required in GCC 56.1 is [insert amount ]. |
| GCC 57.2 (g) | The maximum number of days is: [insert number; consistent with Clause 47.1 on liquidated damages]. |
| GCC 58.1 | The percentage to apply to the value of the work not completed, representing the Employer’s additional cost for completing the Works, is [insert percentage]. |

Section IX - Contract Forms

This Section contains forms which, once completed, will form part of the Contract. The forms for Performance Security and Advance Payment Security, when required, shall only be completed by the successful Bidder after contract award.

Table of Forms

Letter of Acceptance	38

Contract Agreement	39

Performance Security (Bank Guarantee)	41

Performance Security (Performance Bond)	43

Advance Payment Security	45

Letter of Acceptance

[ on letterhead paper of the Employer]

. . . . . . . [date]. . . . . . .

To:	. . . . . . . . . .  [ name and address of the Contractor] . . . . . . . . . .

Subject:	. . . . . . . . . .   [Notification of Award Contract No].  . . . . . . . . . .

This is to notify you that your Bid dated . . . . [insert date] . . . .  for execution of the . . . . . . . . . .[insert name of the contract and identification number, as given in the Appendix to Bid] . . . . . . . . . . for the Accepted Contract Amount of . . . . . . . . .[insert amount in numbers and words and name of currency], as corrected and modified in accordance with the Instructions to Bidders is hereby accepted by our Agency.

You are requested to furnish the Performance Security within 28 days in accordance with the Conditions of Contract, using for that purpose the of the Performance Security Form included in Section IX (Contract Forms) of the Bidding Document.

[Choose one of the following statements:]

We accept that __________________________[insert the name of Adjudicator proposed by the Bidder]  be appointed as the Adjudicator.

[or]

We do not accept that _______________________[insert the name of the Adjudicator proposed by the Bidder] be appointed as the Adjudicator, and by sending a copy of this Letter of Acceptance to ________________________________________[insert name of the Appointing Authority], the Appointing Authority, we are hereby requesting such Authority to appoint the Adjudicator in accordance with ITB 43.1 and GCC 23.1.

Authorized Signature:

Name and Title of Signatory:

Name of Agency:

Attachment:  Contract Agreement

Contract Agreement

THIS AGREEMENT made the . . . . . .day of . . . . . . . . . . . . . . . . ., . . . . . . ., between . . . . . [name of the Employer]. . . . .. . . . . (hereinafter “the Employer”), of the one part, and . . . . . [name of the Contractor]. . . . .(hereinafter “the Contractor”), of the other part:

WHEREAS the Employer desires that the Works known as . . . . . [name of the Contract]. . . . .should be executed by the Contractor, and has accepted a Bid by the Contractor for the execution and completion of these Works and the remedying of any defects therein,

The Employer and the Contractor agree as follows:

1.	In this Agreement words and expressions shall have the same meanings as are respectively assigned to them in the Contract documents referred to.

2.	The following documents shall be deemed to form and be read and construed as part of this Agreement. This Agreement shall prevail over all other Contract documents.

- the Letter of Acceptance

- the addenda Nos ________(if any)

- the  Particular Conditions

- the General Conditions of Contract ;

- the  Contractor’s Bid

- the Specification

- the Drawings

- Bill of Quantities;  and

- any other document listed in the PCC as forming part of the Contract,

3.	In consideration of the payments to be made by the Employer to the Contractor as specified in this Agreement, the Contractor hereby covenants with the Employer to execute the Works and to remedy defects therein in conformity in all respects with the provisions of the Contract.

4.	The Employer hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying of defects therein, the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

IN WITNESS whereof the parties hereto have caused this Agreement to be executed in accordance with the laws of . . . . . [name of the borrowing country]. . . . .on the day, month and year specified above.

| Signed by: |  | Signed by: |  |
| --- | --- | --- | --- |
| for and on behalf of the Employer | for and on behalf the Contractor |
| in the presence of: |  | in the presence of: |  |
| Witness, Name, Signature, Address, Date | Witness, Name, Signature, Address, Date |

Performance Security

Standard Form of a Performance Bond (Performance Security)

Address of guarantor bank: ………………………………………………………………… …………………………………………………………………. …………………………………………………………………..

Address of beneficiary (contracting agency): …………………………………………………………………. ………………………………………………………………….. …………………………………………………………………..

On ...................................... you concluded with ................................................. ("Contractor") a contract for ................................................................. (project, object of contract) at a price of .................................................................

In accordance with the provisions of the contract the Contractor is obligated to provide a performance bond for … % of the contract price.

We, the undersigned ……………………….. (Guarantor), waiving all objections and defences under the aforementioned contract, hereby irrevocably and independently guarantee to pay on your first written demand an amount up to a total of ............................................................... (in words: ................................................................................)

against your written declaration that the Contractor has failed to duly perform the aforementioned contract.

In the event of any claim under this guarantee, payment shall be effected to KfW, Frankfurt am Main (BIC: KFWIDEFF, BLZ 500 204 00), account no. 38 000 000 00 (IBAN: DE53 5002 0400 3800 0000 00) for account of ............................................... (project-executing agency/purchaser).

This guarantee shall expire no later than …………………………………….

By this date we must have received any claims for payment by letter or encoded telecommunication.

It is understood that you will return this guarantee to us on expiry or after payment of the total amount to be claimed hereunder.

This guarantee is governed by the laws of ……………………….

...........................................................			.................................................

Place, date							Guarantor

Bank Guarantee for Advance Payment

Model Advance Payment Bank Guarantee

Address of guarantor bank: ………………………………………………………………… …………………………………………………………………. …………………………………………………………………..

Address of beneficiary (contracting agency): …………………………………………………………………. ………………………………………………………………….. …………………………………………………………………..

On ........................................... you concluded with (name and full address) ........................................................................... ……………………………………………………………………………………………………………………………………………… (“Contractor”) a Contract for ................................................................... (project, subject of Contract) for the sum of

................................................

According to the provisions of the Contract the Contractor receives an advance payment in the amount of ............................ equalling ................................................... percent of the contract price.

We, the undersigned.............................................................................................................. (bank), waiving all objections and defences under the aforementioned Contract, hereby irrevocably and independently guarantee to pay on your first written demand any amount advanced to the Contractor up to a total of

..............................................
(in words: .............................................................)

against your written declaration that the Contractor has failed to perform as stipulated in the aforementioned Contract.

This Guarantee shall enter into force as soon as the advance payment has been credited to the account of the Contractor.

This Guarantee shall be automatically reduced pro rata in accordance with the payments performed.

In the event of any claim under this Guarantee, payment shall be effected to KfW, Frankfurt am Main (JBIC.: KFWIDEFF, BLZ 500 204 00), account no. 38 000 000 00 (IBAN: DE53 5002 0400 3800 0000 00) for the account of .................................................... (Purchaser, project-executing agency).

This guarantee shall expire not later than .......................... by which date we must have received any claims by letter or coded telecommunication

It is understood that you will return this Guarantee to us upon expiry thereof or after settlement of the total amount to be claimed hereunder.

.............................................	...............................................................

Place, date						Guarantor

SAMPLE FORMAT :

Invitation for Bids

[COUNTRY]

[NAME OF PROJECT]

Financing Agreement No.:___________________________

Contract Title: __________________

Reference No. : ___________________

1.	The [insert name of Implementing Entity] [has received/has applied for] financing from the Syria Recovery Trust Fund (SRTF) toward the cost of the [insert name of project or grant], and intends to apply part of the proceeds toward payments under the contract for [insert title of contract].

2. 	The [insert name of implementing agency] now invites sealed bids from eligible bidders for [insert brief description of Works required, including quantities, location, construction period,   etc.].

3. 	Bidding will be conducted through the International Competitive Bidding procedures as specified in the SRTF’s   Procurement Guidelines, and is open to bidders from all countries.

4. 	Interested eligible bidders may obtain further information from [insert name of implementing agency, insert name and e-mail of officer in charge] and inspect the bidding documents during office hours [insert office hours if applicable i.e. 0900 to 1700 hours] at the address given below [state address at the end of this invitation] .

5. 	A complete set of bidding documents in [insert name of language] may be obtained by interested eligible bidders free of charge electronically by downloading from the website www.srtfund.org or upon the submission of a written application to the address below The document will be sent electronically or by regular mail upon specific request of the Applicant .

6. 	Bids must be delivered to the address below [state address at the end of this invitation] on or before [insert time and date]. Electronic bidding will [will not] be permitted. Late bids will be rejected. Bids will be publicly opened in the presence of the bidders’ designated representatives and anyone who choose to attend at the address below [state address at the end of this invitation] on [insert time and date].

7. 	All bids must be accompanied by a Bid Security or Bid Securing Declaration  of [insert amount and currency in case of a Bid Security.

8.	The address(es) referred to above is(are): [insert detailed address(es) ]

[insert name of office, room number]

Attn: [insert name of officer & title]

[insert postal address and/or street address]

[insert postal code, city, country]

Tel: [include the country and city code]

Fax: [include the country and city code]

E-mail: [insert electronic address if electronic bidding is permitted]

Web site:

# Footnotes

Please note: usually the purchaser, the recipient and the beneficiary are the same organisation, however in some cases the procurement procedure will be carried out by the SRTF MU (Employer) on behalf of the beneficiary/recipient organisation(s). In such cases, this information will be provided in the bidding data sheet.

In this context, any action taken by a bidder, supplier, contractor, or any of its personnel, agents, subcontractors, sub-consultants, service providers, suppliers and/or their employees to influence the procurement process or contract execution for undue advantage is improper.

“Another party” refers to a public or private sector official acting in relation to the procurement process or contract execution.  In this context, “ official” includes SRTF and KfW staff and employees of other organizations taking or reviewing procurement decisions.

“Party” refers to a public or private sector official; the terms “benefit” and “obligation” relate to the procurement process or contract execution; and the “act or omission” is intended to influence the procurement process or contract execution.

“Parties” refers to participants in the procurement process (including public officials) attempting to establish bid prices at artificial, non- competitive levels.

“Party” refers to a participant in the procurement process or contract execution.

In lump sum contracts, delete “rates and prices and the” sum price.”

For lump sum contracts, delete “rates and prices and shown in the Schedule of Adjustment Data in the Appendix to Bid are reasonable” and replace with “Lump Sum.”

In lump sum contracts, delete “Bill of Quantities” and replace with “Activity Schedule.”

Daywork is work carried out following instructions of the Project Manager and paid for on the basis of time spent by workers, and the use of materials and the Contractor’s equipment, at the rates quoted in the Bid.  For Daywork to be priced competitively for Bid evaluation purposes, the Employer must list tentative quantities for individual items to be costed against Daywork (e.g., a specific number of tractor driver staff-days, or a specific tonnage of Portland cement), to be multiplied by the bidders’ quoted rates and included in the total Bid price.

Non performance, as decided by the Employer, shall include all contracts where (a) non performance was not challenged by the contractor, including through referral to the dispute resolution mechanism under the respective contract, and (b) contracts that were so challenged but fully settled against the contractor. Non performance shall not include contracts where Employers decision was overruled by the dispute resolution mechanism. Non performance must be based on all information on fully settled disputes or litigation, i.e. dispute or litigation that has been resolved in accordance with the dispute resolution mechanism under the respective contract and where all appeal instances available to the Bidder have been exhausted.

This requirement also applies to contracts executed by the Bidder as JV member.

The Bidder shall provide accurate information on the letter of Bid about any litigation or arbitration resulting from contracts completed or ongoing under its execution over the last five years. A consistent history of court/arbitral awards against the Bidder or any member of a joint venture may result in disqualifying the Bidder.

The similarity shall be based on the physical size, complexity, methods/technology and/or other characteristics described in Section VI, Work’s Requirements. Summation of number of small value contracts (less than the value specified under requirement) to meet the overall requirement will not be accepted.

For contracts under which the Bidder participated as a joint venture member or sub-contractor, only the Bidder’s share, by value, shall be considered to meet this requirement.

In the case of JV, the value of contracts completed by its members shall not be aggregated to determine whether the requirement of the minimum value of a single contract has been met. Instead, each contract performed by each member shall satisfy the minimum value of a single contract as required for single entity. In determining whether the JV meets the requirement of total number of contracts, only the number of contracts completed by all members each of value equal or more than the minimum value required shall be aggregated.

In case of Lump Sum Contract, use Sample Activity Schedule.

If the most recent set of financial statements is for a period earlier than 12 months from the date of bid, the reason for this should be justified.

In lump sum contracts, delete “Bill of Quantities” and replace with “Activity Schedule.”

In this context, any action taken by a bidder, supplier, contractor, or any of its personnel, agents, subcontractors, sub-consultants, service providers, suppliers and/or their employees to influence the procurement process or contract execution for undue advantage is improper.

“Another party” refers to a public or private sector official acting in relation to the procurement process or contract execution.  In this context, “official” includes SRTF and KfW staff and employees of other organizations taking or reviewing procurement decisions.

“Party” refers to a public or private sector official; the terms “benefit” and “obligation” relate to the procurement process or contract execution; and the “act or omission” is intended to influence the procurement process or contract execution.

“Parties” refers to participants in the procurement process (including public officials) attempting to establish bid prices at artificial, non- competitive levels.

“Party” refers to a participant in the procurement process or contract execution.

In lump sum contracts, delete “Bill of Quantities” and replace with “Activity Schedule,” and replace GCC Sub-Clauses 36.1 and 36.2, as follows:

36.1	The Contractor shall provide updated Activity Schedules within 14 days of being instructed to by the Project Manager.  The activities on the Activity Schedule shall be coordinated with the activities on the Program.

36.2	The Contractor shall show delivery of Materials to the Site separately on the Activity Schedule if payment for Materials on Site shall be made separately.

In lump sum contracts, delete “Bill of Quantities” and replace with “Activity Schedule,” and replace entire GCC Clause 37 with new GCC Sub-Clause 37.1, as follows:

37.1	The Activity Schedule shall be amended by the Contractor to accommodate changes of Program or method of working made at the Contractor’s own discretion.  Prices in the Activity Schedule shall not be altered when the Contractor makes such changes to the Activity Schedule.

In lump sum contracts, add “and Activity Schedules” after “Programs.”

In lump sum contracts, delete this paragraph.

In lump sum contracts, add “or Activity Schedule” after “Program.”

In lump sum contracts, replace this paragraph with the following:  “The value of work executed shall comprise the value of completed activities in the Activity Schedule.”

In lump sum contracts, delete “Bill of Quantities” and replace with “Activity Schedule.”

A brief description of the type(s) of  Works should be provided, including quantities, location of Project, construction period, application of margin of preference and other information necessary to enable potential bidders to decide whether or not to respond to the Invitation.  Bidding Documents may require bidders to have specific experience or capabilities; such qualification requirements should also be included in this paragraph.

The office for inquiry and issuance of bidding documents and that for bid submission may or may not be the same.

Substitute the address for bid submission if it is different from address for inquiry and issuance of bidding documents.